# Railway Maintenance Block Planning: Development Playbook

Project: Adaptive Hybrid Scheduling for Railway Maintenance Block Planning (DAA) | Stack: Python 3.10+, pytest, OR-Tools CP-SAT, Streamlit | Source: your project spec PDF (Problem Statement to Validation Strategy)

## 0. Read This First

### 0.1 Missing or ambiguous information (decide before the milestone listed)

The spec leaves these points open. Each has a default used throughout this playbook. If your team picks differently, change the default and re-check the milestone named in the last column.

| # | Open point | Default used here | Decide before |
| --- | --- | --- | --- |
| D1 | Selector routing rule. PDF p.7 diagram says: score <= threshold -> exact (WIS-DP if simplified, else ILP); score > threshold -> CA-GREEDY. PDF p.14 text says: exact DP for simplified, CA-GREEDY for complex, ILP for validation only. | Follow the p.7 diagram, behind config flag exact_route_for_extended: ilp (set none to follow p.14) | 8.2 |
| D2 | Threshold is called 'learned' but the selector is 'not a machine-learning model'. | Thresholds and alpha weights are calibrated by grid search on a calibration seed set and stored in config/threshold.json. No ML library. | 8.3 |
| D3 | Time model | Integer minutes, half-open intervals [start, end), default horizon 1440 | 1.1 |
| D4 | Task weight formula | w = 10*criticality + urgency, both integers 1-5. Integer weights keep optimum comparisons exact. | 1.1 |
| D5 | Asset conflict (C3) compatibility | Any two tasks on the same asset are incompatible (no compatibility matrix) | 2.1 |
| D6 | Dependency semantics (C5) | A task may be scheduled only if all prerequisites are scheduled and finished. Dependency graph must be acyclic. | 2.1 |
| D7 | Resource model (C4) | Each resource type has integer capacity and availability intervals. A task demands integer units for its whole duration. | 2.1 |
| D8 | 'Simplified case' definition | One corridor, one resource type with capacity 1, every task demands 1, window length == duration (fixed interval), no trains blocking, no dependencies | 3.1 |
| D9 | Git hosting and team workflow | GitHub; Rishi pushes phase branches; main receives merges only at a phase Go decision; CI = GitHub Actions | 0.1 |
| D10 | CA-GREEDY term formulas and lambda values | Defined in Milestone 5.2 | 5.2 |
| D11 | Experiment sizes and time limits | Oracle n<=16; gap studies n=20-200; scalability to n=5000; ILP limit 30 s, 1 worker | 9.1 |
| D12 | NAIVE-GREEDY dependency handling | Single pass in priority order; skip a task if its prerequisites are not already placed | 5.1 |

### 0.2 Working conventions

Package layout (src layout, package name rbp):

railway-scheduler/
  src/rbp/
    models/        # Task, Corridor, Resource, Timetable, Instance, Schedule, Interval
    io/            # input checks, JSON/CSV load and save
    constraints/   # C1-C5 predicates used BY algorithms
    validation/    # independent validator (never imports constraints/)
    generation/    # synthetic generators
    algorithms/    # wis_dp, brute_force, naive_greedy, ca_greedy, ilp_exact, placement
    selector/      # features, selector, calibration
    metrics/
    experiments/
    api.py         # thin facade, the only module the UI imports
  app/streamlit_app.py
  config/defaults.yaml, config/threshold.json
  scripts/  tests/  docs/  reports/  results/ (ignored)

Import rules (enforced by a test in 0.3): models imports nothing from rbp. validation imports only models. constraints and algorithms may import models and constraints. app imports only rbp.api. This is what makes the validator independent and keeps scheduling logic out of the UI.

Git workflow. One branch per phase (phase-N-topic). One commit per milestone plus an annotated tag cp-N.M. Push only after every test and verification item passes. At the phase Go decision, merge into main with --no-ff and tag phase-N-complete.

Status legend for test tables: ☐ not run, ✅ pass, ❌ fail. Fill it in as you go.

Global rollback recipes (milestones refer to these by name):

- R1, not yet pushed: git reset --hard HEAD~1 (drops the last commit and its changes).

- R2, pushed: git revert <sha> then git push origin <branch>. Never force-push a shared branch.

- R3, several bad commits: git revert --no-commit cp-N.M..HEAD && git commit -m "revert: return to cp-N.M" && git push origin <branch>

- R4, inspect a stable point: git switch -c recovery/cp-N.M cp-N.M

Never commit (global): .venv/, __pycache__/, .pytest_cache/, .ruff_cache/, .coverage, htmlcov/, results/, data/generated/, *.log, .env, .streamlit/secrets.toml, IDE folders. This project needs no API keys; if one ever appears, it goes in .env, which stays ignored.

# Phase 0: Project Setup and Baseline

## Milestone 0.1: Repository skeleton and environment

Depends on: nothing.

1. Milestone Name: Reproducible repo and Python environment.

2. Objective: A fresh clone installs with one command, imports rbp, and runs a passing smoke test. Every later milestone builds on this.

3. Tasks to Complete

- ☐ Create the folder and repo: mkdir railway-scheduler && cd railway-scheduler && git init -b main && git checkout -b phase-0-setup

- ☐ Create venv: python3.10 -m venv .venv then activate (source .venv/bin/activate, or .venv\\Scripts\\activate on Windows)

- ☐ pip install pytest pytest-cov ruff pyyaml ortools streamlit pandas matplotlib

- ☐ Write requirements.txt with the exact versions you installed (pip freeze, keep only these top-level packages pinned)

- ☐ Write pyproject.toml (requires-python = ">=3.10", package rbp under src/) and run pip install -e .

- ☐ Create every folder in the layout above with an __init__.py where it is a package

- ☐ Add .gitignore (list in 0.2) and a README stub

- ☐ Add tests/test_smoke.py asserting import rbp works

4. Files / Modules Affected: pyproject.toml, requirements.txt, .gitignore, README.md, src/rbp/**/__init__.py, tests/test_smoke.py.

5. Implementation Guidance: Use the src layout so tests import the installed package, not the working directory by accident. Why each dependency: pytest (automated testing requirement), pytest-cov (coverage evidence), ruff (one tool for lint and import order), pyyaml (defaults.yaml), ortools (CP-SAT baseline), streamlit (prototype), pandas (results tables and UI tables), matplotlib (Gantt charts and experiment plots). Algorithms use only stdlib (random, bisect, heapq), so numpy is not a declared dependency.

6. Test Cases

| ID | Test Scenario | Preconditions | Steps | Expected Result | Status |
| --- | --- | --- | --- | --- | --- |
| T0.1-01 | Clean install | Fresh clone, new venv | pip install -r requirements.txt && pip install -e . | Exit code 0 | ☐ |
| T0.1-02 | Package import | Installed | python -c "import rbp" | No error | ☐ |
| T0.1-03 | Smoke test | Installed | pytest | 1 passed | ☐ |
| T0.1-04 | ortools works | Installed | python -c "from ortools.sat.python import cp_model" | No error | ☐ |
| T0.1-05 | Ignored files stay out | venv exists | git status | .venv/ not listed | ☐ |
| T0.1-06 | Unsupported Python (negative) | Python 3.9 available | pip install -e . under 3.9 | Install refused (requires-python) | ☐ |

7. Verification Checklist

- ☐ T0.1-01 to T0.1-06 pass

- ☐ git ls-files shows no .venv, no cache folders

- ☐ pip freeze versions match requirements.txt for top-level packages

8. Milestone Completion Criteria: DONE when a teammate can clone, install and run pytest green using only the README stub.

9. Git Checkpoint

git remote add origin <your-repo-url>
git status
git add .
git commit -m "chore: repo skeleton, environment and smoke test"
git push -u origin phase-0-setup
git tag -a cp-0.1 -m "Milestone 0.1 stable" && git push origin cp-0.1

Do NOT commit: .venv/, caches, .env.

10. Rollback / Recovery: Nothing earlier exists. Before push use R1. After push on this private branch: git push origin --delete phase-0-setup, then redo the milestone.

## Milestone 0.2: Test, lint and CI pipeline

Depends on: 0.1.

1. Milestone Name: Automated checks (pytest, ruff, CI).

2. Objective: Every push is checked automatically, so no broken checkpoint can pass unnoticed.

3. Tasks to Complete

- ☐ Add [tool.pytest.ini_options] to pyproject.toml: testpaths=["tests"], addopts="-q --strict-markers", markers slow and ortools

- ☐ Add [tool.ruff] config (line length 100, rules E,F,I)

- ☐ Add scripts/check.sh running ruff check . && pytest -m "not slow"

- ☐ Add .github/workflows/ci.yml (below)

- ☐ Enable branch protection so main requires CI to pass (if using GitHub)

4. Files / Modules Affected: pyproject.toml, scripts/check.sh, .github/workflows/ci.yml.

5. Implementation Guidance: Keep CI identical to the local check script so results never differ. The slow marker separates the 100-seed gates and scalability runs, which run before every phase merge but not on every push.

name: ci
on: [push, pull_request]
jobs:
  test:
    runs-on: ubuntu-latest
    steps:
      - uses: actions/checkout@v4
      - uses: actions/setup-python@v5
        with: {python-version: '3.10'}
      - run: pip install -r requirements.txt && pip install -e .
      - run: ruff check .
      - run: pytest -m 'not slow'

6. Test Cases

| ID | Test Scenario | Preconditions | Steps | Expected Result | Status |
| --- | --- | --- | --- | --- | --- |
| T0.2-01 | Local check passes | Clean tree | bash scripts/check.sh | Exit 0 | ☐ |
| T0.2-02 | Failing test is caught (negative) | Temp test assert False | Run check, then delete the test | Exit non-zero, then 0 | ☐ |
| T0.2-03 | Lint error is caught (negative) | Add unused import | ruff check . | Error F401 reported | ☐ |
| T0.2-04 | Unknown marker rejected | Test uses @pytest.mark.typo | pytest | Error under --strict-markers | ☐ |
| T0.2-05 | CI runs on push | Branch pushed | Open Actions tab | Green run for the commit | ☐ |
| T0.2-06 | Slow tests deselected | One test marked slow | pytest -m "not slow" | Slow test not run | ☐ |

7. Verification Checklist

- ☐ CI shows green for the pushed commit

- ☐ A deliberately failing push turns CI red (then reverted)

- ☐ scripts/check.sh matches CI steps

8. Milestone Completion Criteria: DONE when CI is green on phase-0-setup and both negative checks (T0.2-02, T0.2-03) behaved correctly.

9. Git Checkpoint

git status
git add .
git commit -m "ci: pytest, ruff and GitHub Actions pipeline"
git push origin phase-0-setup
git tag -a cp-0.2 -m "Milestone 0.2 stable" && git push origin cp-0.2

Do NOT commit the temporary failing test or the unused import used for T0.2-02/03.

10. Rollback / Recovery: Bad workflow file: git revert <sha-of-0.2> (R2) and push; previous stable point is cp-0.1.

## Milestone 0.3: Config, seed policy and architecture guard

Depends on: 0.2.

1. Milestone Name: Central config, deterministic RNG and import-boundary test.

2. Objective: One validated config source, a seeding policy that guarantees reproducibility, and an automated guard for the separation rules in 0.2.

3. Tasks to Complete

- ☐ Write config/defaults.yaml (below) and a placeholder config/threshold.json ({"version":0,"threshold":0.5,"alpha":[0.2,0.2,0.2,0.2,0.2]})

- ☐ Implement rbp/config.py: load_config(path) with key and type checks, ConfigError

- ☐ Implement rbp/rng.py: make_rng(seed, stream) returning random.Random seeded from f"{seed}:{stream}"

- ☐ Write tests/test_import_boundaries.py (AST scan of src/rbp for forbidden imports)

- ☐ Write docs/ARCHITECTURE.md (layer diagram from spec section 6 plus the import rules)

horizon: 1440
seeds: {gate: [0, 99], calibration: [1000, 1099], evaluation: [2000, 2099]}
selector: {alpha: [0.2, 0.2, 0.2, 0.2, 0.2], n_ref: 200, exact_route_for_extended: ilp}
ca_greedy: {lambda_block: 1.0, lambda_resource: 0.5, lambda_conflict: 0.5, lookahead_k: 20}
ilp: {time_limit_s: 30, workers: 1, seed: 0}

4. Files / Modules Affected: config/defaults.yaml, config/threshold.json, src/rbp/config.py, src/rbp/rng.py, tests/test_config.py, tests/test_rng.py, tests/test_import_boundaries.py, docs/ARCHITECTURE.md.

5. Implementation Guidance: Separate seed ranges for gate, calibration and evaluation prevent the selector from being tuned on the instances it is later evaluated on. Named RNG streams (tasks, trains, deps) mean adding a new random draw in one generator stage does not shift every other stage's output, which protects reproducibility. Use only stdlib random.

6. Test Cases

| ID | Test Scenario | Preconditions | Steps | Expected Result | Status |
| --- | --- | --- | --- | --- | --- |
| T0.3-01 | Load valid config | Default file | load_config(...) | Dict with all keys, correct types | ☐ |
| T0.3-02 | Missing key (negative) | Remove horizon in temp copy | Load | ConfigError naming horizon | ☐ |
| T0.3-03 | Wrong type (validation) | horizon: abc | Load | ConfigError | ☐ |
| T0.3-04 | Alpha must sum to 1 | alpha sums to 0.9 | Load | ConfigError | ☐ |
| T0.3-05 | RNG determinism | none | make_rng(7,'tasks') twice, draw 5 values | Identical sequences | ☐ |
| T0.3-06 | RNG stream isolation | none | make_rng(7,'tasks') vs make_rng(7,'trains') | Sequences differ | ☐ |
| T0.3-07 | Boundary test passes | Current code | pytest tests/test_import_boundaries.py | Pass | ☐ |
| T0.3-08 | Boundary violation detected (negative) | Feed checker source from rbp.constraints import x labelled as validation/ | Run checker function | Violation reported | ☐ |

7. Verification Checklist

- ☐ All T0.3 tests pass and scripts/check.sh is green

- ☐ Changing a seed in the config changes RNG output; same seed repeats it

- ☐ docs/ARCHITECTURE.md lists the import rules exactly as in 0.2

8. Milestone Completion Criteria: DONE when config loads with validation, RNG determinism tests pass, and the boundary test is part of the default pytest run.

9. Git Checkpoint

git status
git add .
git commit -m "feat(core): validated config, seeded RNG streams, import-boundary test"
git push origin phase-0-setup
git tag -a cp-0.3 -m "Milestone 0.3 stable" && git push origin cp-0.3

Do NOT commit machine-specific config overrides (config/local.yaml; add it to .gitignore).

10. Rollback / Recovery: git revert <sha-of-0.3> (R2); previous stable point cp-0.2.

## Phase 0 Completion Checkpoint

| Item | Record |
| --- | --- |
| Completed milestones | 0.1, 0.2, 0.3 |
| Tests passed | pytest result line: ____ passed; ruff check . clean |
| Known issues | ____ |
| Git commit / hash | git rev-parse --short HEAD = ____; tag phase-0-complete |
| Overall phase verification | Fresh clone, install, bash scripts/check.sh green; CI green |
| Go / No-Go for Phase 1 | GO only if every box above is filled and D3, D4 are decided |

git switch main && git merge --no-ff phase-0-setup -m "merge: phase 0"
git push origin main
git tag -a phase-0-complete -m "Phase 0 done" && git push origin phase-0-complete
git switch -c phase-1-data-model

# Phase 1: Data Model, Input Validation and I/O

## Milestone 1.1: Domain models

Depends on: Phase 0 complete; decisions D3, D4.

1. Milestone Name: Immutable domain entities.

2. Objective: Represent tasks, corridors, assets, resources, train timetable, instances and schedules (functional requirement 2).

3. Tasks to Complete

- ☐ Interval(start, end) helper with half-open overlaps()

- ☐ Task (frozen dataclass): id, corridor_id, asset_id, window_start, window_end, duration, criticality, urgency, demands: dict[str,int], depends_on: tuple[int,...], property weight = 10*criticality + urgency

- ☐ Corridor (id, traffic_level, asset_ids), Resource (type, capacity, availability: tuple[Interval,...]), TrainInterval and Timetable (corridor_id, sorted intervals)

- ☐ Instance (tasks, corridors, resources, timetable, horizon, meta) with lookup by id

- ☐ Schedule (starts: dict[task_id, start]) with end_of(task) helper

4. Files / Modules Affected: src/rbp/models/{interval,task,corridor,resource,timetable,instance,schedule}.py, tests/test_models.py.

5. Implementation Guidance: Frozen dataclasses prevent algorithms from mutating shared inputs. Half-open intervals mean a task ending at 100 and one starting at 100 do not conflict, which is the convention every constraint and the validator must share. Models contain no validation logic; that is Milestone 1.2.

6. Test Cases

| ID | Test Scenario | Preconditions | Steps | Expected Result | Status |
| --- | --- | --- | --- | --- | --- |
| T1.1-01 | Weight formula | Task crit 3, urg 1 | Read weight | 31 | ☐ |
| T1.1-02 | Immutability | Task built | Assign task.duration = 5 | FrozenInstanceError | ☐ |
| T1.1-03 | Touching intervals | [0,5) and [5,9) | overlaps() | False | ☐ |
| T1.1-04 | Overlap by one unit (edge) | [0,5) and [4,9) | overlaps() | True | ☐ |
| T1.1-05 | Nested and identical | [0,10) vs [2,3); [1,4) vs [1,4) | overlaps() | True for both | ☐ |
| T1.1-06 | Instance lookup | 3 tasks | instance.task(2) | Correct task; unknown id raises KeyError | ☐ |
| T1.1-07 | Schedule end | Task start 10, duration 7 | end_of | 17 | ☐ |

7. Verification Checklist

- ☐ T1.1 tests pass; models imports nothing else from rbp (boundary test green)

- ☐ Weight formula matches decision D4 as recorded in the README

8. Milestone Completion Criteria: DONE when all entities exist, are immutable, and the interval convention is documented in a docstring.

9. Git Checkpoint

git status
git add .
git commit -m "feat(models): immutable domain entities and interval semantics"
git push origin phase-1-data-model
git tag -a cp-1.1 -m "Milestone 1.1 stable" && git push origin cp-1.1

10. Rollback / Recovery: git revert <sha-of-1.1> (R2); previous stable phase-0-complete.

## Milestone 1.2: Input validation

Depends on: 1.1.

1. Milestone Name: Instance input checks (functional requirement 3).

2. Objective: Reject malformed instances with precise, collected error codes before any algorithm sees them.

3. Tasks to Complete

- ☐ validate_instance(instance) -> list[InputError] returning all errors, not just the first

- ☐ Implement codes: E_DURATION (<=0), E_WINDOW (window shorter than duration), E_HORIZON (window outside [0,horizon]), E_DUP_ID, E_UNKNOWN_REF (corridor, asset, resource type), E_DEMAND (demand > capacity), E_RANGE (criticality or urgency outside 1-5), E_DEP_UNKNOWN, E_DEP_SELF, E_DEP_CYCLE (Kahn topological check), E_TRAIN_BAD (start >= end)

- ☐ InstanceError exception wrapping the list for callers that want to raise

4. Files / Modules Affected: src/rbp/io/input_checks.py, tests/test_input_checks.py.

5. Implementation Guidance: Returning a list lets the UI show every problem at once. Cycle detection runs once here so algorithms may assume an acyclic dependency graph. Window shorter than duration is an error, not a warning, because such a task can never satisfy C1.

6. Test Cases

| ID | Test Scenario | Preconditions | Steps | Expected Result | Status |
| --- | --- | --- | --- | --- | --- |
| T1.2-01 | Valid instance | Hand-built fixture | Validate | Empty list | ☐ |
| T1.2-02 | Zero or negative duration | duration 0 | Validate | E_DURATION | ☐ |
| T1.2-03 | Window equals duration (edge) | window 10..20, duration 10 | Validate | No error | ☐ |
| T1.2-04 | Window shorter than duration | window 10..19, duration 10 | Validate | E_WINDOW | ☐ |
| T1.2-05 | Window beyond horizon | window_end 1500, horizon 1440 | Validate | E_HORIZON | ☐ |
| T1.2-06 | Duplicate ids | two tasks id 4 | Validate | E_DUP_ID | ☐ |
| T1.2-07 | Unknown corridor and resource | refs to missing ids | Validate | Both E_UNKNOWN_REF reported | ☐ |
| T1.2-08 | Demand above capacity | demand 3, capacity 2 | Validate | E_DEMAND | ☐ |
| T1.2-09 | Dependency cycle A->B->A | two tasks | Validate | E_DEP_CYCLE | ☐ |
| T1.2-10 | Self dependency | task depends on itself | Validate | E_DEP_SELF | ☐ |
| T1.2-11 | Multiple faults at once | 3 different faults | Validate | 3 distinct codes returned | ☐ |

7. Verification Checklist

- ☐ Every code has at least one failing-fixture test

- ☐ Validating a 5000-task fixture finishes in under 1 s

8. Milestone Completion Criteria: DONE when each listed code is produced by a test and valid fixtures return an empty list.

9. Git Checkpoint

git status
git add .
git commit -m "feat(io): instance input validation with error codes"
git push origin phase-1-data-model
git tag -a cp-1.2 -m "Milestone 1.2 stable" && git push origin cp-1.2

10. Rollback / Recovery: git revert <sha-of-1.2> (R2); previous stable cp-1.1.

## Milestone 1.3: JSON and CSV load and save

Depends on: 1.1, 1.2.

1. Milestone Name: Instance serialization (functional requirement 1, load part).

2. Objective: Save and load instances losslessly so experiments and the UI can share them.

3. Tasks to Complete

- ☐ instance_to_dict, instance_from_dict, save_json, load_json with schema_version: 1

- ☐ CSV directory format (tasks.csv, corridors.csv, resources.csv, trains.csv) via save_csv_dir, load_csv_dir

- ☐ Loaders call validate_instance and raise InstanceError if invalid

- ☐ InstanceLoadError for unreadable or malformed files

- ☐ Golden fixture tests/data/tiny_instance.json

4. Files / Modules Affected: src/rbp/io/serialize.py, tests/data/tiny_instance.json, tests/test_serialize.py.

5. Implementation Guidance: JSON is the authoritative format (nested demands and dependencies); CSV exists for spreadsheet inspection, with demands encoded as type:units;type:units and dependencies as ;-separated ids. Use stdlib json and csv, no extra dependency. Sort keys on save so identical instances produce identical files (needed for the golden hash test in 3.3).

6. Test Cases

| ID | Test Scenario | Preconditions | Steps | Expected Result | Status |
| --- | --- | --- | --- | --- | --- |
| T1.3-01 | JSON round trip | Golden fixture | load, save, load | Instances equal | ☐ |
| T1.3-02 | CSV round trip | Golden fixture | save_csv_dir, load_csv_dir | Instances equal | ☐ |
| T1.3-03 | Malformed JSON (failure) | File with truncated JSON | load_json | InstanceLoadError | ☐ |
| T1.3-04 | Missing field | Remove duration | load | InstanceLoadError naming the field | ☐ |
| T1.3-05 | Unknown schema version | schema_version: 99 | load | Clear error | ☐ |
| T1.3-06 | Invalid but well-formed data | duration -1 | load | InstanceError with E_DURATION | ☐ |
| T1.3-07 | Windows line endings and UTF-8 | CSV saved with CRLF | load | Loads correctly | ☐ |
| T1.3-08 | Deterministic output | Save twice | Compare bytes | Identical | ☐ |
| T1.3-09 | Regression of 1.2 | none | pytest tests/test_input_checks.py | Still passes | ☐ |

7. Verification Checklist

- ☐ All T1.3 tests pass; round trips are exact equality, not approximate

- ☐ Corrupt files never produce a partial instance

8. Milestone Completion Criteria: DONE when JSON and CSV both round-trip the golden fixture and every failure mode raises a named exception.

9. Git Checkpoint

git status
git add .
git commit -m "feat(io): JSON and CSV instance loaders with validation"
git push origin phase-1-data-model
git tag -a cp-1.3 -m "Milestone 1.3 stable" && git push origin cp-1.3

Do NOT commit large generated instance files; only the small golden fixture belongs in tests/data/.

10. Rollback / Recovery: git revert <sha-of-1.3> (R2); previous stable cp-1.2.

## Phase 1 Completion Checkpoint

| Item | Record |
| --- | --- |
| Completed milestones | 1.1, 1.2, 1.3 |
| Tests passed | pytest ____ passed |
| Known issues | ____ |
| Git commit / hash | ____; tag phase-1-complete |
| Overall phase verification | Load golden fixture, validate, save, reload in a fresh interpreter |
| Go / No-Go for Phase 2 | GO only if all tests green, boundary test green, D5-D7 decided |

git switch main && git merge --no-ff phase-1-data-model -m "merge: phase 1"
git push origin main
git tag -a phase-1-complete -m "Phase 1 done" && git push origin phase-1-complete
git switch -c phase-2-constraints

# Phase 2: Constraint Predicates and Independent Validator

## Milestone 2.1: Constraint predicates C1-C5 and placement state

Depends on: Phase 1 complete; decisions D5, D6, D7.

1. Milestone Name: Algorithm-side constraint checks.

2. Objective: One tested set of predicates (C1 time window, C2 train conflict, C3 asset conflict, C4 resource capacity, C5 dependencies) that all algorithms use to decide whether a placement is feasible (functional requirement 4).

3. Tasks to Complete

- ☐ PlacementState: placed starts dict, per-asset sorted placed intervals, per-resource-type usage list of length horizon, with place(task, start) and unplace(task)

- ☐ c1_window_ok, c2_train_ok, c3_asset_ok, c4_resource_ok, c5_dependency_ok

- ☐ is_feasible(instance, state, task, start) -> bool and first_violation(...) -> 'C1'..'C5' | None

- ☐ Merge each resource's availability intervals once at state creation

4. Files / Modules Affected: src/rbp/constraints/predicates.py, src/rbp/constraints/state.py, tests/test_predicates.py.

5. Implementation Guidance: The per-minute usage list makes C4 an O(duration) check and place an O(duration) update; this is simple and fast enough for horizon 1440 and n up to a few thousand. Revisit only if profiling in Phase 9 shows it dominates. C4 also requires the whole interval to lie inside the resource's availability. C5 requires every prerequisite to be placed with end <= start (D6). Check order for first_violation is C1 to C5 so error reporting is deterministic.

6. Test Cases

| ID | Test Scenario | Preconditions | Steps | Expected Result | Status |
| --- | --- | --- | --- | --- | --- |
| T2.1-01 | C1 start at window start | window 100..200, d=50 | start=100 | OK | ☐ |
| T2.1-02 | C1 end exactly at window end (edge) | same | start=150 | OK | ☐ |
| T2.1-03 | C1 end one past window end | same | start=151 | C1 | ☐ |
| T2.1-04 | C1 start before window | same | start=99 | C1 | ☐ |
| T2.1-05 | C2 touching a train interval | train [140,150), task [100,140) | check | OK | ☐ |
| T2.1-06 | C2 overlap by one unit | train [139,150), task [100,140) | check | C2 | ☐ |
| T2.1-07 | C2 train on another corridor | train on corridor 2 | check task on corridor 1 | OK | ☐ |
| T2.1-08 | C3 adjacent tasks same asset | placed [0,10), new [10,20) | check | OK | ☐ |
| T2.1-09 | C3 overlap same asset | placed [0,10), new [9,19) | check | C3 | ☐ |
| T2.1-10 | C3 overlap different asset | same times, other asset | check | OK | ☐ |
| T2.1-11 | C4 capacity exactly met | cap 2, one placed, new demand 1 | check | OK | ☐ |
| T2.1-12 | C4 capacity exceeded by one | cap 2, two placed overlapping | new demand 1 | C4 | ☐ |
| T2.1-13 | C4 outside availability | availability [0,60) | task [50,70) | C4 | ☐ |
| T2.1-14 | C5 start equals prerequisite end | prereq [0,30) | start=30 | OK | ☐ |
| T2.1-15 | C5 start before prerequisite end | prereq [0,30) | start=29 | C5 | ☐ |
| T2.1-16 | C5 prerequisite not placed | none placed | check dependent | C5 | ☐ |
| T2.1-17 | place then unplace | state with usage | place, unplace | Usage and per-asset lists identical to before | ☐ |
| T2.1-18 | Regression of Phase 1 | none | pytest tests/test_models.py tests/test_input_checks.py tests/test_serialize.py | Pass | ☐ |

7. Verification Checklist

- ☐ Every predicate has at least one pass and one fail boundary test

- ☐ first_violation returns the lowest-numbered failing constraint

- ☐ constraints does not import validation or algorithms (boundary test)

8. Milestone Completion Criteria: DONE when all T2.1 tests pass and place/unplace round-trips leave no residue.

9. Git Checkpoint

git status
git add .
git commit -m "feat(constraints): C1-C5 predicates and placement state"
git push origin phase-2-constraints
git tag -a cp-2.1 -m "Milestone 2.1 stable" && git push origin cp-2.1

10. Rollback / Recovery: git revert <sha-of-2.1> (R2); previous stable phase-1-complete.

## Milestone 2.2: Independent constraint validator

Depends on: 1.1 only (deliberately NOT on 2.1 code).

1. Milestone Name: Independent schedule validator (functional requirement 6).

2. Objective: Verify any generated schedule against C1-C5 using separately written logic, so a bug in the predicates cannot hide itself.

3. Tasks to Complete

- ☐ validate_schedule(instance, schedule) -> ValidationReport with valid, violations (each: code, task ids, detail) and counts_by_code

- ☐ C1 by direct comparison; C2 by sorted train starts per corridor plus bisect; C3 by grouping per asset, sorting by start and tracking running maximum end; C4 by a sweep line over +demand/-demand events (ends processed before starts at the same time) plus availability coverage; C5 by direct end/start comparison and prerequisite presence

- ☐ Structural checks: unknown task id (S_UNKNOWN), non-integer start (S_FORMAT)

- ☐ Report all violations, not just the first

4. Files / Modules Affected: src/rbp/validation/validator.py, src/rbp/validation/report.py, tests/test_validator.py.

5. Implementation Guidance: Independence is a design requirement from spec section 9.2. Different algorithms for the same checks (sweep line versus per-minute array, running-max versus placed-list scan) make coincident bugs unlikely. The validator imports only models. The differential comparison between validator and predicates is added in Milestone 3.3, once random instances exist.

6. Test Cases

| ID | Test Scenario | Preconditions | Steps | Expected Result | Status |
| --- | --- | --- | --- | --- | --- |
| T2.2-01 | Valid hand-built schedule | Fixture | Validate | valid=True, no violations | ☐ |
| T2.2-02 | Empty schedule | Any instance | Validate | Valid | ☐ |
| T2.2-03 | Mutation: start outside window | Valid schedule, shift one task | Validate | C1 with that task id | ☐ |
| T2.2-04 | Mutation: overlap a train | Move task onto train interval | Validate | C2 | ☐ |
| T2.2-05 | Mutation: two tasks overlap on asset | Move one | Validate | C3 listing both ids | ☐ |
| T2.2-06 | Mutation: exceed capacity | Overlap 3 tasks with cap 2 | Validate | C4 | ☐ |
| T2.2-07 | Mutation: dependent before prerequisite end | Move dependent earlier | Validate | C5 | ☐ |
| T2.2-08 | Dependent scheduled, prerequisite missing | Remove prerequisite | Validate | C5 | ☐ |
| T2.2-09 | Touching intervals accepted (edge) | Tasks [0,10), [10,20) same asset | Validate | Valid | ☐ |
| T2.2-10 | Capacity exactly met accepted | cap 2, two overlapping | Validate | Valid | ☐ |
| T2.2-11 | Several violations at once | Break C1, C3, C5 | Validate | All three codes reported | ☐ |
| T2.2-12 | Unknown task id (failure) | Schedule has id 999 | Validate | S_UNKNOWN, no crash | ☐ |
| T2.2-13 | Independence | none | Boundary test plus grep | validation/ imports only models | ☐ |

7. Verification Checklist

- ☐ Each of C1-C5 is caught by a mutation test

- ☐ Boundary test proves no import from constraints or algorithms

- ☐ Validating 5000 placed tasks takes under 1 s

8. Milestone Completion Criteria: DONE when all mutation tests pass and independence is machine-checked.

9. Git Checkpoint

git status
git add .
git commit -m "feat(validation): independent C1-C5 schedule validator"
git push origin phase-2-constraints
git tag -a cp-2.2 -m "Milestone 2.2 stable" && git push origin cp-2.2

10. Rollback / Recovery: git revert <sha-of-2.2> (R2); previous stable cp-2.1.

## Phase 2 Completion Checkpoint

| Item | Record |
| --- | --- |
| Completed milestones | 2.1, 2.2 |
| Tests passed | pytest ____ passed |
| Known issues | ____ |
| Git commit / hash | ____; tag phase-2-complete |
| Overall phase verification | Hand-built schedules give the same verdict from predicates and validator on all fixtures |
| Go / No-Go for Phase 3 | GO only if all mutation tests pass and independence is machine-checked |

git switch main && git merge --no-ff phase-2-constraints -m "merge: phase 2"
git push origin main
git tag -a phase-2-complete -m "Phase 2 done" && git push origin phase-2-complete
git switch -c phase-3-generator

# Phase 3: Synthetic Data Generator

## Milestone 3.1: Simplified-instance generator

Depends on: Phase 2 complete; decision D8.

1. Milestone Name: Reproducible simplified instances for WIS-DP.

2. Objective: Generate single-corridor, single-resource, fixed-interval instances with a controllable overlap level, plus a predicate is_simplified.

3. Tasks to Complete

- ☐ is_simplified(instance) in models/simplified.py implementing D8

- ☐ generate_simplified(n, seed, horizon=1440, overlap_factor=0.5, dmin=10, dmax=120): duration uniform in [dmin, dmax]; start uniform in [0, span-d] where span = max(dmax, round(horizon*(1 - 0.9*overlap_factor))); window = [start, start+d]; criticality and urgency uniform 1-5; one corridor, one asset, resource crew capacity 1 demand 1

- ☐ Output passes validate_instance

- ☐ CLI scripts/gen_instances.py --kind simplified --n 50 --seed 1 --out data/generated/s1.json

4. Files / Modules Affected: src/rbp/generation/simplified.py, src/rbp/models/simplified.py, scripts/gen_instances.py, tests/test_gen_simplified.py.

5. Implementation Guidance: Smaller span packs the same number of tasks into less time, which raises overlap; that is the only knob WIS-DP experiments need. Use make_rng(seed, 'tasks') (Milestone 0.3). Output goes to data/generated/, which is gitignored.

6. Test Cases

| ID | Test Scenario | Preconditions | Steps | Expected Result | Status |
| --- | --- | --- | --- | --- | --- |
| T3.1-01 | Determinism | none | Generate twice, seed 5 | Byte-identical JSON | ☐ |
| T3.1-02 | Different seeds differ | none | Seeds 5 and 6 | Different task sets | ☐ |
| T3.1-03 | Valid and simplified | 50 seeds | validate_instance, is_simplified | No errors, True | ☐ |
| T3.1-04 | Window equals duration | n=100 | Check all tasks | window length == duration | ☐ |
| T3.1-05 | Duration bounds | dmin=10, dmax=120 | Check all | All within bounds | ☐ |
| T3.1-06 | n=0 and n=1 (edge) | none | Generate | Valid empty / single | ☐ |
| T3.1-07 | Negative n (failure) | none | n=-1 | ValueError | ☐ |
| T3.1-08 | Overlap factor monotonic | 20 seeds | Mean pairwise-overlap fraction at 0.1 vs 0.9 | Higher at 0.9 | ☐ |
| T3.1-09 | Scale | n=10000 | Time generation | Under 2 s | ☐ |
| T3.1-10 | Extended instance is not simplified | hand-built fixture with 2 corridors | is_simplified | False | ☐ |

7. Verification Checklist

- ☐ All T3.1 pass; two runs of the CLI with one seed produce identical files

- ☐ data/generated/ not tracked by Git

8. Milestone Completion Criteria: DONE when determinism, validity and the overlap trend all pass.

9. Git Checkpoint

git status
git add .
git commit -m "feat(generation): deterministic simplified instance generator"
git push origin phase-3-generator
git tag -a cp-3.1 -m "Milestone 3.1 stable" && git push origin cp-3.1

Do NOT commit anything under data/generated/.

10. Rollback / Recovery: git revert <sha-of-3.1> (R2); previous stable phase-2-complete.

## Milestone 3.2: Extended generator with controlled correlations

Depends on: 3.1, 1.3.

1. Milestone Name: Multi-corridor, multi-resource instances with trains and dependencies.

2. Objective: Generate realistic instances (spec section 7) including the controlled correlations: urgency with narrower and earlier windows, criticality with asset impact, traffic with asset impact, department with resource type, peak hours with denser trains.

3. Tasks to Complete

- ☐ Corridors: traffic level low/medium/high; 3-6 assets each; per-asset impact 1-5 stored in instance.meta['asset_impact'], biased up by traffic level

- ☐ Resources: one type per department (track, signal, power, civil), capacity 1-3, availability covering at least 70% of the horizon; department kept as a latent generator variable that selects the task's resource type

- ☐ Timetable per corridor: headway by traffic (low 90, medium 45, high 25 minutes), train occupancy 5-10 minutes, headway halved in peak bands, headway x4 in the night band 0-300

- ☐ Tasks: criticality = clipped round(asset impact + noise); urgency drives window slack (higher urgency, smaller slack) and earlier window start; durations 10-60

- ☐ Dependencies: with probability 0.15 a task gets 1-2 prerequisites chosen from earlier-windowed tasks, kept only if the dependent window can still hold prerequisite plus itself

- ☐ Feasibility sanity: every task must have at least one start passing C1, C2 and resource availability; otherwise widen its window to the nearest train gap that fits (up to 20 tries), else drop and log it

- ☐ Separate RNG streams: corridors, resources, trains, tasks, deps

4. Files / Modules Affected: src/rbp/generation/extended.py, scripts/gen_instances.py (add --kind extended), tests/test_gen_extended.py.

5. Implementation Guidance: Without the night band and the feasibility sanity step, high-traffic corridors have no gap long enough for any task and instances degenerate. Correlation strength is a generator parameter, not a hard-coded constant. Record the numeric thresholds you finally use in docs/GENERATOR.md.

6. Test Cases

| ID | Test Scenario | Preconditions | Steps | Expected Result | Status |
| --- | --- | --- | --- | --- | --- |
| T3.2-01 | Valid instances | 50 seeds | validate_instance | No errors | ☐ |
| T3.2-02 | Determinism | none | Generate twice | Byte-identical | ☐ |
| T3.2-03 | Urgency vs slack | 20 seeds pooled | Spearman correlation | Negative, below -0.2 | ☐ |
| T3.2-04 | Traffic vs asset impact | 20 seeds | Mean impact high vs low corridors | Higher for high traffic | ☐ |
| T3.2-05 | Peak vs off-peak trains | 10 seeds | Trains per hour | Peak greater | ☐ |
| T3.2-06 | Department to resource | n=200 | Check mapping | Each department uses its own type | ☐ |
| T3.2-07 | Dependencies acyclic | 50 seeds | Kahn check | No cycle; edges respect window order | ☐ |
| T3.2-08 | Demand within capacity | 50 seeds | Check | All demands <= capacity | ☐ |
| T3.2-09 | Each task individually placeable | 50 seeds | C1, C2, availability scan | 100% | ☐ |
| T3.2-10 | Invalid parameters (failure) | none | n_corridors=0 | ValueError | ☐ |
| T3.2-11 | JSON round trip | 5 seeds | save, load | Equal instance | ☐ |
| T3.2-12 | Regression | none | pytest tests/test_gen_simplified.py | Pass | ☐ |

7. Verification Checklist

- ☐ All T3.2 pass; correlation thresholds recorded in docs/GENERATOR.md

- ☐ Dropped-task count per instance logged and under 5% on default parameters

8. Milestone Completion Criteria: DONE when instances are valid, deterministic, correlated as specified, and every task is individually placeable.

9. Git Checkpoint

git status
git add .
git commit -m "feat(generation): extended generator with correlations, trains, dependencies"
git push origin phase-3-generator
git tag -a cp-3.2 -m "Milestone 3.2 stable" && git push origin cp-3.2

10. Rollback / Recovery: git revert <sha-of-3.2> (R2); previous stable cp-3.1.

## Milestone 3.3: Difficulty knobs, determinism lock and validator-versus-predicate fuzz

Depends on: 3.2, 2.1, 2.2.

1. Milestone Name: Controlled difficulty plus the first cross-check of the two constraint implementations.

2. Objective: Expose parameters that control conflict density, resource contention, window tightness and corridor load (spec section 4.1 item 7), lock generator output against accidental change, and differentially test predicates against the independent validator.

3. Tasks to Complete

- ☐ Params: window_slack_factor, assets_per_corridor (fewer assets means more conflicts), resource_capacity_scale, corridor_load (share of time occupied by tasks)

- ☐ Proxy functions in the test helpers: same-asset window-overlap fraction, demand-minutes over capacity-minutes, mean duration over window length, (task plus train minutes) over corridor minutes

- ☐ tests/data/golden_hashes.json with SHA-256 of generated JSON for fixed seeds

- ☐ Differential fuzz test: build random partial schedules by repeatedly adding tasks that is_feasible accepts, then probe random (task, start) pairs

4. Files / Modules Affected: src/rbp/generation/extended.py, tests/test_gen_knobs.py, tests/test_golden_hashes.py, tests/test_predicates_vs_validator.py, tests/data/golden_hashes.json.

5. Implementation Guidance: The golden hash test fails on any RNG change, which protects the spec requirement 'deterministic results for the same seed'. Changing a hash needs a deliberate commit with the words regenerate golden in the message. The fuzz test is the payoff of independent validation: for a probe, is_feasible must equal the validator's verdict on the schedule extended by that placement.

6. Test Cases

| ID | Test Scenario | Preconditions | Steps | Expected Result | Status |
| --- | --- | --- | --- | --- | --- |
| T3.3-01 | Slack knob | 20 seeds | Low vs high slack | Tightness proxy decreases as slack rises | ☐ |
| T3.3-02 | Asset-count knob | 20 seeds | 6 vs 2 assets | Conflict proxy higher with 2 | ☐ |
| T3.3-03 | Capacity knob | 20 seeds | Scale 2.0 vs 0.5 | Contention proxy lower at 2.0 | ☐ |
| T3.3-04 | Load knob | 20 seeds | Low vs high load | Utilization proxy higher | ☐ |
| T3.3-05 | Golden hashes | Pinned seeds | Generate, hash | Matches stored | ☐ |
| T3.3-06 | Golden failure detection (negative) | Temporarily alter an RNG stream name | Run test | Fails; then revert | ☐ |
| T3.3-07 | Predicate versus validator | 20 instances, 200 probes each | Compare verdicts | 0 disagreements | ☐ |
| T3.3-08 | Failure injection | Temporarily change C3 to <= in predicates | Run T3.3-07 | Disagreement found; then revert | ☐ |

7. Verification Checklist

- ☐ T3.3-07 shows 0 disagreements over at least 4000 probes

- ☐ Both injected-failure checks failed as expected and were reverted (git diff clean)

8. Milestone Completion Criteria: DONE when knobs move their proxies in the right direction, hashes are pinned, and fuzz agreement is complete.

9. Git Checkpoint

git status
git add .
git commit -m "feat(generation): difficulty knobs, golden hashes, predicate-validator fuzz"
git push origin phase-3-generator
git tag -a cp-3.3 -m "Milestone 3.3 stable" && git push origin cp-3.3

Do NOT commit leftover temporary failure-injection edits.

10. Rollback / Recovery: git revert <sha-of-3.3> (R2); previous stable cp-3.2.

## Phase 3 Completion Checkpoint

| Item | Record |
| --- | --- |
| Completed milestones | 3.1, 3.2, 3.3 |
| Tests passed | pytest ____ passed |
| Known issues | ____ |
| Git commit / hash | ____; tag phase-3-complete |
| Overall phase verification | Generate 100 simplified and 100 extended instances; all valid; fuzz 0 disagreements |
| Go / No-Go for Phase 4 | GO only if golden hashes are pinned and fuzz is clean |

git switch main && git merge --no-ff phase-3-generator -m "merge: phase 3"
git push origin main
git tag -a phase-3-complete -m "Phase 3 done" && git push origin phase-3-complete
git switch -c phase-4-wis-dp

# Phase 4: WIS-DP and the Brute-Force Correctness Gate

## Milestone 4.1: WIS-DP implementation

Depends on: 3.1.

1. Milestone Name: Exact Weighted Interval Scheduling by dynamic programming.

2. Objective: Solve simplified instances optimally in O(n log n) time and O(n) space (spec section 8.2).

3. Tasks to Complete

- ☐ AlgoResult dataclass in algorithms/base.py: name, schedule, objective, meta

- ☐ solve_wis_dp(instance); raise NotSimplifiedError unless is_simplified

- ☐ Sort by (end, start, id); compute p[i] = bisect_right(ends, start_i); OPT[i] = max(OPT[i-1], w_i + OPT[p[i]])

- ☐ Reconstruct by walking back; tie rule: take a task only if strictly better than excluding it

- ☐ Return Schedule with start = window start

4. Files / Modules Affected: src/rbp/algorithms/base.py, src/rbp/algorithms/wis_dp.py, tests/test_wis_dp.py.

5. Implementation Guidance: bisect_right (not bisect_left) is what makes touching intervals compatible. The strict-improvement tie rule makes the output deterministic. The function must not mutate the instance.

6. Test Cases

Hand fixture (window = duration): A [0,3) w15, B [2,5) w21, C [4,7) w14, D [6,9) w23, E [8,10) w13. Expected p = A0, B0, C1, D2, E3; OPT = 15, 21, 29, 44, 44.

| ID | Test Scenario | Preconditions | Steps | Expected Result | Status |
| --- | --- | --- | --- | --- | --- |
| T4.1-01 | Hand example | Fixture above | Solve | Objective 44, tasks {B, D} | ☐ |
| T4.1-02 | p(i) values | Fixture | Inspect meta | As listed | ☐ |
| T4.1-03 | Empty instance | n=0 | Solve | Objective 0, empty schedule | ☐ |
| T4.1-04 | Single task | n=1 | Solve | That task chosen | ☐ |
| T4.1-05 | All overlapping | 5 identical windows | Solve | Only the heaviest chosen | ☐ |
| T4.1-06 | All disjoint | 5 spaced tasks | Solve | All chosen | ☐ |
| T4.1-07 | Touching intervals | [0,5), [5,9) | Solve | Both chosen | ☐ |
| T4.1-08 | Equal weights tie | Two equal options | Solve twice | Identical schedule | ☐ |
| T4.1-09 | Not simplified (failure) | Extended instance | Solve | NotSimplifiedError | ☐ |
| T4.1-10 | Output valid | 50 generated instances | Run independent validator | All valid | ☐ |
| T4.1-11 | Input not mutated | any | Compare instance before and after | Equal | ☐ |
| T4.1-12 | Scalability (slow) | n=100000 | Time | Completes in seconds; time(2n)/time(n) about 2 to 2.5 | ☐ |

7. Verification Checklist

- ☐ Hand-computed OPT table matches the implementation's table

- ☐ Validator accepts every produced schedule

8. Milestone Completion Criteria: DONE when T4.1-01 to T4.1-11 pass. The brute-force gate (4.3) is still required before this phase can close.

9. Git Checkpoint

git status
git add .
git commit -m "feat(algorithms): WIS-DP exact solver for simplified instances"
git push origin phase-4-wis-dp
git tag -a cp-4.1 -m "Milestone 4.1 stable" && git push origin cp-4.1

10. Rollback / Recovery: git revert <sha-of-4.1> (R2); previous stable phase-3-complete.

## Milestone 4.2: Brute-force oracle

Depends on: 3.1 (not on WIS-DP code).

1. Milestone Name: Exhaustive ground-truth solver for small simplified instances.

2. Objective: Provide an optimum that shares no code with WIS-DP (spec section 9.1).

3. Tasks to Complete

- ☐ solve_brute_force(instance, max_n=20): enumerate all 2^n subsets, accept a subset only if no pair overlaps, keep the maximum weight

- ☐ Overlap test written inline as a.start < b.end and b.start < a.end (do not import the DP or predicates)

- ☐ Refuse n > max_n with ValueError; refuse non-simplified instances

4. Files / Modules Affected: src/rbp/algorithms/brute_force.py, tests/test_brute_force.py.

5. Implementation Guidance: Precompute a conflict bitmask per task and check mask & conflict[i] while building subsets. The oracle compares objective values, not subsets, because several optimal subsets may exist.

6. Test Cases

| ID | Test Scenario | Preconditions | Steps | Expected Result | Status |
| --- | --- | --- | --- | --- | --- |
| T4.2-01 | Hand example | Fixture from 4.1 | Solve | 44 | ☐ |
| T4.2-02 | Empty and single | n=0, n=1 | Solve | 0; the task | ☐ |
| T4.2-03 | All overlapping | 6 tasks | Solve | Max single weight | ☐ |
| T4.2-04 | All disjoint | 6 tasks | Solve | Sum of weights | ☐ |
| T4.2-05 | Size limit (failure) | n=21 | Solve | ValueError | ☐ |
| T4.2-06 | Touching intervals | [0,5), [5,9) | Solve | Both chosen | ☐ |
| T4.2-07 | Output valid | 30 instances n<=12 | Validator | All valid | ☐ |
| T4.2-08 | Runtime (slow) | n=16 | Time | Under 10 s | ☐ |

7. Verification Checklist

- ☐ brute_force.py has no import of wis_dp or constraints (grep)

- ☐ Hand example matches 44

8. Milestone Completion Criteria: DONE when T4.2 passes and independence is confirmed.

9. Git Checkpoint

git status
git add .
git commit -m "feat(algorithms): brute-force oracle for small simplified instances"
git push origin phase-4-wis-dp
git tag -a cp-4.2 -m "Milestone 4.2 stable" && git push origin cp-4.2

10. Rollback / Recovery: git revert <sha-of-4.2> (R2); previous stable cp-4.1.

## Milestone 4.3: Mandatory correctness gate (100 of 100)

Depends on: 4.1, 4.2, 2.2.

1. Milestone Name: WIS-DP equals brute force on 100 random instances plus adversarial families.

2. Objective: The spec's mandatory gate: Brute Force = WIS-DP on 100 / 100 random simplified instances.

3. Tasks to Complete

- ☐ tests/test_gate_wis_vs_bruteforce.py: seeds 0-99, n random in 1-16, overlap factor random; assert objectives equal

- ☐ For each case also assert: DP schedule passes the independent validator, and the objective recomputed from the schedule equals the reported objective

- ☐ Adversarial families: all overlapping, chain of touching tasks, nested intervals, equal end times, equal weights, identical intervals, long low-weight task versus several short high-weight ones

- ☐ scripts/gate_wis.py printing GATE wis-dp vs brute-force: 100/100

- ☐ Append the result, date and commit hash to docs/validation_log.md

4. Files / Modules Affected: tests/test_gate_wis_vs_bruteforce.py, scripts/gate_wis.py, docs/validation_log.md.

5. Implementation Guidance: No tolerance is allowed because weights are integers. If any case fails, fix the DP or the oracle; never weaken the gate. Seeds 0-99 come from seeds.gate in the config.

6. Test Cases

| ID | Test Scenario | Preconditions | Steps | Expected Result | Status |
| --- | --- | --- | --- | --- | --- |
| T4.3-01 | Random gate | Seeds 0-99 | Run gate | 100/100 equal | ☐ |
| T4.3-02 | Adversarial families | 7 families x 5 sizes | Run | All equal | ☐ |
| T4.3-03 | DP schedules validated | all gate cases | Validator | 0 violations | ☐ |
| T4.3-04 | Reported equals recomputed objective | all gate cases | Recompute from schedule | Equal | ☐ |
| T4.3-05 | Gate detects a bug (negative) | Temporarily switch bisect_right to bisect_left | Run gate | Gate FAILS; revert afterwards | ☐ |
| T4.3-06 | Regression | none | Full pytest | Pass | ☐ |

7. Verification Checklist

- ☐ Output line reads exactly 100/100

- ☐ T4.3-05 failed as expected and git diff shows no leftover edit

- ☐ docs/validation_log.md contains the result with the commit hash

8. Milestone Completion Criteria: DONE only when the gate prints 100/100 and the injected bug is detected.

9. Git Checkpoint

git status
git add .
git commit -m "test(algorithms): WIS-DP vs brute-force gate 100/100"
git push origin phase-4-wis-dp
git tag -a cp-4.3 -m "Milestone 4.3 stable: gate passed" && git push origin cp-4.3

10. Rollback / Recovery: If a later change breaks the gate, git switch -c recovery/cp-4.3 cp-4.3 (R4) to compare, then fix forward or use R2 on the offending commit.

## Phase 4 Completion Checkpoint

| Item | Record |
| --- | --- |
| Completed milestones | 4.1, 4.2, 4.3 |
| Tests passed | pytest ____ passed; gate 100/100 |
| Known issues | ____ |
| Git commit / hash | ____; tag phase-4-complete |
| Overall phase verification | python scripts/gate_wis.py prints 100/100 on a fresh clone |
| Go / No-Go for Phase 5 | GO only if the gate is 100/100 (hard requirement) |

git switch main && git merge --no-ff phase-4-wis-dp -m "merge: phase 4"
git push origin main
git tag -a phase-4-complete -m "Phase 4 done" && git push origin phase-4-complete
git switch -c phase-5-greedy

# Phase 5: Greedy Heuristics (NAIVE-GREEDY and CA-GREEDY)

## Milestone 5.1: Placement engine and NAIVE-GREEDY baseline

Depends on: Phase 4 complete (2.1 predicates, 2.2 validator); decision D12.

1. Milestone Name: Earliest-feasible-start engine plus the baseline heuristic.

2. Objective: Provide the shared placement helpers and a fast baseline against which CA-GREEDY is measured (spec section 8.3).

3. Tasks to Complete

- ☐ algorithms/placement.py: event_starts(instance, state, task) returning the sorted unique starts from: window start; end of each train interval on the corridor; end of each placed task on the same asset; end of each placed task sharing a demanded resource type; end of each prerequisite; start of each availability interval of demanded types; all clipped to [window_start, window_end - duration]

- ☐ earliest_feasible_start(instance, state, task) -> int | None scanning event_starts with is_feasible

- ☐ solve_naive_greedy(instance): order by (higher weight, shorter duration, lower id); place at earliest feasible start; skip if none

- ☐ Dependency rule (D12): single pass; a task is placed only if all prerequisites are already placed

- ☐ No look-ahead and no resource reasoning, exactly as the spec says

4. Files / Modules Affected: src/rbp/algorithms/placement.py, src/rbp/algorithms/naive_greedy.py, tests/test_placement.py, tests/test_naive_greedy.py.

5. Implementation Guidance: The earliest feasible start is always the window start or the moment some blocking interval ends, which is why scanning event points is exact and avoids scanning every integer minute. This claim is verified by a brute-force scan test below. The single-pass dependency rule is a deliberate baseline weakness (a dependent with higher weight than its prerequisite is skipped); document it in the README.

6. Test Cases

| ID | Test Scenario | Preconditions | Steps | Expected Result | Status |
| --- | --- | --- | --- | --- | --- |
| T5.1-01 | Ordering | Tasks with equal weights, different durations | Inspect processing order | Weight desc, duration asc, id asc | ☐ |
| T5.1-02 | Free slot | No conflicts | Solve | Each task at window start | ☐ |
| T5.1-03 | Train blocks start | Train [0,20) at window start | Solve | Start = 20 | ☐ |
| T5.1-04 | Window too small after trains | Gap shorter than duration | Solve | Task skipped | ☐ |
| T5.1-05 | Capacity forces delay | cap 1, two tasks same window | Solve | Second starts at end of first (if window allows) | ☐ |
| T5.1-06 | Dependent with heavier weight | Dependent weight > prerequisite | Solve | Dependent skipped (prerequisite not yet placed) | ☐ |
| T5.1-07 | Dependent with lighter weight | Prerequisite heavier | Solve | Both placed, dependent after prerequisite end | ☐ |
| T5.1-08 | Events equal brute scan | 200 random probes on small instances | Compare earliest_feasible_start with integer scan | Identical | ☐ |
| T5.1-09 | Determinism | none | Run twice | Identical schedule | ☐ |
| T5.1-10 | Validity | 50 extended instances | Independent validator | 0 violations | ☐ |
| T5.1-11 | Never beats optimum | 50 simplified instances | Compare with WIS-DP | naive <= DP | ☐ |
| T5.1-12 | Empty instance and input immutability | n=0 | Solve | Empty schedule; instance unchanged | ☐ |
| T5.1-13 | Regression | none | pytest earlier phases | Pass | ☐ |

7. Verification Checklist

- ☐ T5.1-08 shows 0 mismatches (this proves the event-point argument)

- ☐ If any naive objective exceeds WIS-DP on simplified data, stop: there is a bug in one of them

8. Milestone Completion Criteria: DONE when all T5.1 tests pass and the engine matches brute-force scanning.

9. Git Checkpoint

git status
git add .
git commit -m "feat(algorithms): placement engine and NAIVE-GREEDY baseline"
git push origin phase-5-greedy
git tag -a cp-5.1 -m "Milestone 5.1 stable" && git push origin cp-5.1

10. Rollback / Recovery: git revert <sha-of-5.1> (R2); previous stable phase-4-complete.

## Milestone 5.2: CA-GREEDY scoring components and candidate placements

Depends on: 5.1; decision D10.

1. Milestone Name: Look-ahead scoring terms for conflict-aware placement.

2. Objective: Implement and unit-test the four score terms (base priority, blocking penalty, resource-fit bonus, conflict-creation penalty) before assembling the algorithm (spec section 8.4).

3. Tasks to Complete

- ☐ ca_candidates(instance, state, task, lookahead): event_starts plus the latest start, plus for each look-ahead task u on the same asset the starts u.window_end and u.window_start - duration (flush alignments), keeping only feasible starts

- ☐ lookahead_set(instance, state): top lookahead_k unscheduled tasks by weight

- ☐ Tentatively place the candidate, measure, then unplace (state must be restored exactly)

- ☐ Terms, with count_feasible(u) = number of feasible candidate starts of u: blocking B = sum of w_u over look-ahead tasks whose count drops from at least 1 to 0; conflict C = sum of w_u x (1 - after/before) over tasks whose count drops but stays above 0; fit R in [0,1] = mean over demanded types of mean (usage before placement over the interval / capacity)

- ☐ Score = w_t - lambda_b*B + lambda_r*w_t*R - lambda_c*C with lambdas from config

4. Files / Modules Affected: src/rbp/algorithms/ca_terms.py, tests/test_ca_terms.py.

5. Implementation Guidance: These formulas are the D10 default; the spec only gives the general form. Blocking and conflict-creation are kept distinct on purpose: blocking is a task lost completely, conflict-creation is a task squeezed. Fit favours packing into already-busy resource periods, which leaves idle stretches contiguous for other tasks. Cost per candidate is O(k x m) where m is candidate starts per look-ahead task; lookahead_k bounds it. Record the final lambdas and the reason in docs/CA_GREEDY.md after tuning in 5.3.

6. Test Cases

Hand fixture F (one asset, no resources): X weight 31 (criticality 3, urgency 1), window [0,6), duration 2. Y weight 21, fixed [0,2). Z weight 21, fixed [2,4). With lambda_b=1, nothing placed.

| ID | Test Scenario | Preconditions | Steps | Expected Result | Status |
| --- | --- | --- | --- | --- | --- |
| T5.2-01 | Candidates for X | Fixture F | ca_candidates(X) | {0, 2, 4} | ☐ |
| T5.2-02 | Blocking at start 0 | F | Evaluate | B = 21 (kills Y) | ☐ |
| T5.2-03 | Blocking at start 4 | F | Evaluate | B = 0 | ☐ |
| T5.2-04 | Scores | F | Score X at 0, 2, 4 | 10, 10, 31 | ☐ |
| T5.2-05 | Conflict-creation | u has 5 feasible starts, placement removes 2 | Evaluate | C = w_u x 2/5 | ☐ |
| T5.2-06 | Fit term | One type, cap 2, usage 1 over interval | Evaluate | R = 0.5 | ☐ |
| T5.2-07 | Lookahead off | lookahead_k=0 | Evaluate | B = C = 0, score = w_t (+ fit) | ☐ |
| T5.2-08 | Lookahead cap | k=3, 10 unscheduled | Count tasks inspected | At most 3 | ☐ |
| T5.2-09 | State restored | any | Evaluate, compare state before and after | Identical usage arrays and per-asset lists | ☐ |
| T5.2-10 | No feasible candidate (failure) | Task with window blocked by train | Candidates | Empty list, no exception | ☐ |
| T5.2-11 | Regression | none | pytest tests/test_placement.py | Pass | ☐ |

7. Verification Checklist

- ☐ Hand-computed scores 10, 10, 31 reproduced

- ☐ State-restoration test passes under 100 random evaluations

8. Milestone Completion Criteria: DONE when each term has a hand-computed test and evaluation never alters the state.

9. Git Checkpoint

git status
git add .
git commit -m "feat(algorithms): CA-GREEDY scoring terms and candidate generation"
git push origin phase-5-greedy
git tag -a cp-5.2 -m "Milestone 5.2 stable" && git push origin cp-5.2

10. Rollback / Recovery: git revert <sha-of-5.2> (R2); previous stable cp-5.1.

## Milestone 5.3: CA-GREEDY algorithm and baseline comparison

Depends on: 5.2.

1. Milestone Name: Complete conflict-aware greedy scheduler.

2. Objective: Build the full CA-GREEDY schedule (spec section 8.4) and show on held-out data that it is a valid, deterministic improvement over the baseline.

3. Tasks to Complete

- ☐ solve_ca_greedy(instance, config): keep a priority queue of ready tasks (all prerequisites placed) keyed by (higher weight, shorter duration, lower id); pop, evaluate candidates, place at the highest score (tie: earliest start); newly ready dependents join the queue

- ☐ A task with no feasible candidate is rejected permanently, and its dependents are rejected too

- ☐ Config switch allow_skip_negative (default False) for later ablation

- ☐ Tune lambdas on calibration seeds (1000-1099) only; record choice and comparison table in docs/CA_GREEDY.md

4. Files / Modules Affected: src/rbp/algorithms/ca_greedy.py, config/defaults.yaml (lambdas), docs/CA_GREEDY.md, tests/test_ca_greedy.py.

5. Implementation Guidance: CA-GREEDY uses the same ordering key as NAIVE-GREEDY, so setting every lambda to 0 must reproduce the baseline on dependency-free instances; this is the regression anchor. It does not guarantee optimality (spec, Main algorithms section); never describe it as optimal in docs or the UI.

6. Test Cases

| ID | Test Scenario | Preconditions | Steps | Expected Result | Status |
| --- | --- | --- | --- | --- | --- |
| T5.3-01 | Fixture F | Fixture from 5.2 | Run both | NAIVE objective 52 (X at 0, Y lost, Z placed); CA objective 73 (X at 4) | ☐ |
| T5.3-02 | Validity | 100 extended instances | Independent validator | 0 violations | ☐ |
| T5.3-03 | Determinism | none | Run twice | Identical schedules | ☐ |
| T5.3-04 | Lambdas zero equals baseline | Instances without dependencies | CA with all lambdas 0 vs naive | Identical objectives | ☐ |
| T5.3-05 | Dependency chain, light prerequisite | prerequisite weight < dependent weight | Run | Both placed; naive places only the prerequisite | ☐ |
| T5.3-06 | Prerequisite infeasible | prerequisite blocked by trains | Run | Prerequisite and dependent both rejected | ☐ |
| T5.3-07 | Mean quality | Calibration seeds 1000-1029 | Compare mean objective | CA mean >= naive mean; win/tie/loss recorded | ☐ |
| T5.3-08 | Small-instance sanity | Simplified, n<=12 | Compare with WIS-DP | CA <= DP | ☐ |
| T5.3-09 | Scale (slow) | n=2000, 5 corridors | Time | Completes under 60 s | ☐ |
| T5.3-10 | Regression | none | Full pytest | Pass | ☐ |

7. Verification Checklist

- ☐ T5.3-01 gives exactly 52 and 73

- ☐ docs/CA_GREEDY.md states lambdas, tuning seeds and the win/tie/loss table

- ☐ Evaluation seeds (2000-2099) were not used for tuning

8. Milestone Completion Criteria: DONE when all tests pass and CA mean objective is at least the baseline mean on calibration seeds. If it is not, adjust terms or lambdas and re-run; do not weaken the test.

9. Git Checkpoint

git status
git add .
git commit -m "feat(algorithms): CA-GREEDY with look-ahead scoring and tuning notes"
git push origin phase-5-greedy
git tag -a cp-5.3 -m "Milestone 5.3 stable" && git push origin cp-5.3

10. Rollback / Recovery: git revert <sha-of-5.3> (R2); previous stable cp-5.2.

## Phase 5 Completion Checkpoint

| Item | Record |
| --- | --- |
| Completed milestones | 5.1, 5.2, 5.3 |
| Tests passed | pytest ____ passed |
| Known issues | ____ |
| Git commit / hash | ____; tag phase-5-complete |
| Overall phase verification | 100 extended instances: 0 violations for both heuristics; CA vs naive table recorded |
| Go / No-Go for Phase 6 | GO only if 0 violations and the lambda tuning notes exist |

git switch main && git merge --no-ff phase-5-greedy -m "merge: phase 5"
git push origin main
git tag -a phase-5-complete -m "Phase 5 done" && git push origin phase-5-complete
git switch -c phase-6-ilp

# Phase 6: ILP-EXACT Reference Baseline (OR-Tools CP-SAT)

## Milestone 6.1: CP-SAT model

Depends on: Phase 5 complete; decisions D5-D7.

1. Milestone Name: Exact solver for the extended problem.

2. Objective: An exact reference and validation baseline (spec section 8.5), not the project's main contribution.

3. Tasks to Complete

- ☐ Per task: present BoolVar; start IntVar whose domain is built with cp_model.Domain.FromIntervals from the contiguous start ranges that satisfy C1, C2 and resource availability (tasks with an empty domain get present = 0)

- ☐ NewOptionalFixedSizeIntervalVar(start, duration, present)

- ☐ C3: AddNoOverlap per asset

- ☐ C4: AddCumulative per resource type with the task demands and capacity

- ☐ C5: present[t] <= present[j] and start[t] >= start[j] + d_j enforced if present[t]

- ☐ Objective: maximize the sum of weight * present

- ☐ Parameters from config: max_time_in_seconds, num_workers = 1, random_seed

- ☐ Return AlgoResult with meta holding status, best_bound, optimal (True only for status OPTIMAL)

4. Files / Modules Affected: src/rbp/algorithms/ilp_exact.py, tests/test_ilp_exact.py (mark ortools).

5. Implementation Guidance: Handling C2 and availability through the start domain, rather than extra constraints, keeps the model small and exact. num_workers = 1 with a fixed seed makes runs repeatable. The empty schedule is always feasible, so status INFEASIBLE signals a modelling bug; raise an error instead of returning it. A FEASIBLE (time-limited) result is a lower bound, so it is never counted as a genuine optimum.

6. Test Cases

| ID | Test Scenario | Preconditions | Steps | Expected Result | Status |
| --- | --- | --- | --- | --- | --- |
| T6.1-01 | Simplified hand example | Fixture from 4.1 | Solve | OPTIMAL, objective 44 | ☐ |
| T6.1-02 | Empty instance | n=0 | Solve | Objective 0 | ☐ |
| T6.1-03 | Train forces later start | Train at window start | Solve | Start after train end | ☐ |
| T6.1-04 | Capacity forces sequencing | cap 1, two overlapping tasks, wide windows | Solve | Both scheduled without overlap | ☐ |
| T6.1-05 | Asset conflict | Two fixed tasks on same asset overlapping | Solve | Heavier chosen | ☐ |
| T6.1-06 | Dependency | Dependent heavier than prerequisite | Solve | Both placed in order, or neither if impossible | ☐ |
| T6.1-07 | Impossible task | Window fully blocked | Solve | Task absent, no error | ☐ |
| T6.1-08 | Time limit hit (failure handling) | n=300, limit 0.05 s | Solve | optimal=False, schedule valid if present | ☐ |
| T6.1-09 | Repeatability | Same seed, workers 1 | Solve twice | Same objective | ☐ |
| T6.1-10 | Validity | 30 extended instances n<=40 | Independent validator | 0 violations | ☐ |
| T6.1-11 | INFEASIBLE guard | Mock solver status | Call wrapper | Raises explicit error | ☐ |

7. Verification Checklist

- ☐ Every returned schedule passes the independent validator

- ☐ meta['optimal'] is True only for status OPTIMAL

8. Milestone Completion Criteria: DONE when all T6.1 tests pass and time-limited runs are labelled non-optimal.

9. Git Checkpoint

git status
git add .
git commit -m "feat(algorithms): ILP-EXACT CP-SAT reference baseline"
git push origin phase-6-ilp
git tag -a cp-6.1 -m "Milestone 6.1 stable" && git push origin cp-6.1

10. Rollback / Recovery: git revert <sha-of-6.1> (R2); previous stable phase-5-complete.

## Milestone 6.2: Cross-validation of ILP, DP and heuristics

Depends on: 6.1, 4.3, 5.3.

1. Milestone Name: Agreement checks between all exact methods and bounds on heuristics.

2. Objective: Prove the ILP model is correct on the simplified case, then use it as a trusted optimum for the extended case.

3. Tasks to Complete

- ☐ Three-way test on gate seeds 0-99 with n<=14: brute force = WIS-DP = ILP objective

- ☐ Extended-case test on calibration seeds with n<=40 where ILP status is OPTIMAL: ILP >= CA-GREEDY and ILP >= NAIVE-GREEDY

- ☐ Write docs/ilp_crosscheck.md: counts of OPTIMAL runs, mean and worst gap for each heuristic

4. Files / Modules Affected: tests/test_crosscheck_exact.py, docs/ilp_crosscheck.md.

5. Implementation Guidance: If a heuristic ever beats an OPTIMAL ILP, either the ILP model excludes a feasible schedule or the validator and predicates accept an infeasible one. Investigate with the failing seed, validate the heuristic schedule independently, and fix the root cause before moving on.

6. Test Cases

| ID | Test Scenario | Preconditions | Steps | Expected Result | Status |
| --- | --- | --- | --- | --- | --- |
| T6.2-01 | Three-way equality | Seeds 0-99, n<=14 | Compare objectives | 100/100 equal | ☐ |
| T6.2-02 | ILP bounds CA | 50 extended instances, OPTIMAL | Compare | ILP >= CA on all | ☐ |
| T6.2-03 | ILP bounds naive | same | Compare | ILP >= naive on all | ☐ |
| T6.2-04 | Heuristic schedules valid | same | Validator | 0 violations | ☐ |
| T6.2-05 | Non-optimal runs excluded | Force time limit | Build comparison set | Run is not used as optimum | ☐ |
| T6.2-06 | Regression | none | Full pytest -m "not slow" | Pass | ☐ |

7. Verification Checklist

- ☐ T6.2-01 prints 100/100

- ☐ Zero cases where a heuristic exceeds an OPTIMAL ILP

8. Milestone Completion Criteria: DONE when equality is 100/100 and no heuristic beats a proven optimum.

9. Git Checkpoint

git status
git add .
git commit -m "test(algorithms): ILP vs DP vs brute-force and heuristic bound checks"
git push origin phase-6-ilp
git tag -a cp-6.2 -m "Milestone 6.2 stable" && git push origin cp-6.2

10. Rollback / Recovery: git revert <sha-of-6.2> (R2); previous stable cp-6.1.

## Phase 6 Completion Checkpoint

| Item | Record |
| --- | --- |
| Completed milestones | 6.1, 6.2 |
| Tests passed | pytest ____ passed; three-way 100/100 |
| Known issues | ____ |
| Git commit / hash | ____; tag phase-6-complete |
| Overall phase verification | docs/ilp_crosscheck.md filled; time-limit behaviour confirmed |
| Go / No-Go for Phase 7 | GO only if three-way equality is 100/100 |

git switch main && git merge --no-ff phase-6-ilp -m "merge: phase 6"
git push origin main
git tag -a phase-6-complete -m "Phase 6 done" && git push origin phase-6-complete
git switch -c phase-7-metrics

# Phase 7: Metrics

## Milestone 7.1: Metrics module and uniform algorithm runner

Depends on: Phase 6 complete.

1. Milestone Name: Scheduling metrics (functional requirement 7).

2. Objective: One module that computes every metric named in spec section 4.2 and runs any algorithm through the same wrapper, always validating the result.

3. Tasks to Complete

- ☐ objective_value, scheduled_count, weighted_coverage (objective over total weight; 0.0 if total weight is 0), count_coverage

- ☐ optimality_gap(objective, optimum) = (optimum - objective) / optimum; None when the optimum is missing, zero or not genuine

- ☐ Extras: utilization (busy minutes over horizon) and fragmentation (maximal contiguous busy blocks per corridor over scheduled tasks)

- ☐ ALGORITHMS registry: WIS-DP, NAIVE-GREEDY, CA-GREEDY, ILP-EXACT, BRUTE-FORCE

- ☐ run_algorithm(name, instance, repeats=1) -> RunRecord with algo, n, seed, objective, coverage, scheduled, runtime_s (median), violations, status, optimal, gap, anomaly, meta

- ☐ Status values: OK, NOT_APPLICABLE (for example WIS-DP on a non-simplified instance), TIMEOUT, ERROR (exception captured, never crashes the caller)

- ☐ Runtime measured with time.perf_counter()

4. Files / Modules Affected: src/rbp/metrics/metrics.py, src/rbp/metrics/runner.py, tests/test_metrics.py.

5. Implementation Guidance: A genuine optimum comes only from BRUTE-FORCE, WIS-DP on a simplified instance, or ILP with status OPTIMAL; the gap must never be computed against a heuristic. A negative gap sets anomaly=True so experiments surface it instead of hiding it. Metrics import models and validation only, never algorithm internals.

6. Test Cases

| ID | Test Scenario | Preconditions | Steps | Expected Result | Status |
| --- | --- | --- | --- | --- | --- |
| T7.1-01 | Objective | Hand schedule | Compute | Sum of weights | ☐ |
| T7.1-02 | Coverage edges | All scheduled / none / total weight 0 | Compute | 1.0 / 0.0 / 0.0 without error | ☐ |
| T7.1-03 | Gap formula | optimum 44, objective 40 | Compute | 0.0909 (4/44) | ☐ |
| T7.1-04 | Gap undefined | optimum None | Compute | None | ☐ |
| T7.1-05 | Negative gap | objective above optimum | Run | Negative value and anomaly=True | ☐ |
| T7.1-06 | Violation count | Mutated schedule | Run | Matches validator count | ☐ |
| T7.1-07 | Fragmentation | Touching tasks / separated tasks | Compute | 1 block / 2 blocks | ☐ |
| T7.1-08 | Not applicable | WIS-DP on extended instance | Run | Status NOT_APPLICABLE | ☐ |
| T7.1-09 | Error captured | Algorithm raises | Run | Status ERROR, message stored, no crash | ☐ |
| T7.1-10 | Runtime recorded | Sleep fixture 0.05 s | Run | runtime_s >= 0.05 | ☐ |
| T7.1-11 | Repeatability | Same instance | Run twice | All fields equal except runtime | ☐ |
| T7.1-12 | Regression | none | Full pytest -m "not slow" | Pass | ☐ |

7. Verification Checklist

- ☐ Every metric in spec section 4.2 has a function and a test

- ☐ run_algorithm returns a record for every algorithm on a sample instance

8. Milestone Completion Criteria: DONE when the runner handles OK, NOT_APPLICABLE, TIMEOUT and ERROR paths and gap logic only uses genuine optima.

9. Git Checkpoint

git status
git add .
git commit -m "feat(metrics): metrics module and validated algorithm runner"
git push origin phase-7-metrics
git tag -a cp-7.1 -m "Milestone 7.1 stable" && git push origin cp-7.1

10. Rollback / Recovery: git revert <sha-of-7.1> (R2); previous stable phase-6-complete.

## Phase 7 Completion Checkpoint

| Item | Record |
| --- | --- |
| Completed milestones | 7.1 |
| Tests passed | pytest ____ passed |
| Known issues | ____ |
| Git commit / hash | ____; tag phase-7-complete |
| Overall phase verification | run_algorithm on one simplified and one extended sample for every algorithm gives sensible records |
| Go / No-Go for Phase 8 | GO only if error paths are tested and D1, D2 are decided |

git switch main && git merge --no-ff phase-7-metrics -m "merge: phase 7"
git push origin main
git tag -a phase-7-complete -m "Phase 7 done" && git push origin phase-7-complete
git switch -c phase-8-selector

# Phase 8: Adaptive Selector

## Milestone 8.1: Complexity features and score

Depends on: Phase 7 complete; models; generator knobs (3.3).

1. Milestone Name: Five normalized complexity features and the weighted score.

2. Objective: Compute C = a1*f1 + a2*f2 + a3*f3 + a4*f4 + a5*f5 from five features in [0,1] (spec section 8.6).

3. Tasks to Complete

- ☐ features.py with these default definitions (confirm with your team, they are not fixed by the spec): f1 size = min(1, n / n_ref), n_ref = 200; f2 conflict density = overlapping-window pairs among same-asset pairs divided by same-asset pairs (0 if none); f3 resource contention = max over types of min(1, sum of demand x duration / (capacity x available minutes)); f4 time-window tightness = mean of duration / window length (1 means fixed interval); f5 corridor utilization = mean over corridors of min(1, (task minutes + train-occupied minutes) / horizon)

- ☐ f2 computed with a per-asset sweep in O(n log n), plus an O(n^2) reference used only in tests

- ☐ complexity_score(features, alpha); alpha loaded from config/threshold.json, must have 5 entries summing to 1

- ☐ Features dataclass with named fields for later reasoning text

4. Files / Modules Affected: src/rbp/selector/features.py, tests/test_features.py.

5. Implementation Guidance: Features are normalized so no single one dominates before weights are applied. The selector imports models only. Keep each feature a separate pure function so calibration (8.3) and the UI can display them individually.

6. Test Cases

Hand fixture H: horizon 100, one corridor, one train [40,50). Asset A: task 1 window [0,20) d10, task 2 window [10,30) d10. Asset B: task 3 window [0,50) d25, task 4 window [60,80) d20. One resource type, capacity 2, available [0,100), each task demands 1. Equal alpha = 0.2.

| ID | Test Scenario | Preconditions | Steps | Expected Result | Status |
| --- | --- | --- | --- | --- | --- |
| T8.1-01 | Fixture features | H | Compute | f1 0.02, f2 0.50, f3 0.325, f4 0.625, f5 0.75 | ☐ |
| T8.1-02 | Fixture score | H | Compute | 0.444 | ☐ |
| T8.1-03 | Bounds | 200 generated instances | Compute all | Every feature in [0,1] | ☐ |
| T8.1-04 | Empty instance | n=0 | Compute | All features 0, no division error | ☐ |
| T8.1-05 | Size clipping | n=1000, n_ref=200 | Compute f1 | 1.0 | ☐ |
| T8.1-06 | f2 sweep equals brute force | 50 random instances | Compare with O(n^2) count | Identical | ☐ |
| T8.1-07 | Zero availability guard | Resource with no availability but demanded | Compute f3 | 1.0, no crash | ☐ |
| T8.1-08 | Alpha validation (failure) | alpha sums to 0.9 or has 4 entries | Load | Error | ☐ |
| T8.1-09 | Knob monotonicity | 20 seeds | Lower slack factor | f4 increases | ☐ |
| T8.1-10 | Determinism and no mutation | any | Compute twice | Equal; instance unchanged | ☐ |

7. Verification Checklist

- ☐ Hand values reproduced exactly

- ☐ Sweep equals brute-force pair counts on all random cases

8. Milestone Completion Criteria: DONE when features and score match the hand calculation and stay inside [0,1] on generated data.

9. Git Checkpoint

git status
git add .
git commit -m "feat(selector): complexity features and weighted score"
git push origin phase-8-selector
git tag -a cp-8.1 -m "Milestone 8.1 stable" && git push origin cp-8.1

10. Rollback / Recovery: git revert <sha-of-8.1> (R2); previous stable phase-7-complete.

## Milestone 8.2: Routing rule and reasoning output

Depends on: 8.1, 6.1, 5.3, 4.1; decision D1 must be settled.

1. Milestone Name: Threshold-based algorithm selection with an explanation (functional requirement 10).

2. Objective: Pick an algorithm from the score and return a human-readable reason.

3. Tasks to Complete

- ☐ select(instance, config) -> Decision(algorithm, score, features, threshold, reason)

- ☐ Rule (D1 default): if score <= threshold, route to exact: WIS-DP if is_simplified, else ILP-EXACT when exact_route_for_extended = ilp, else CA-GREEDY; if score > threshold, route to CA-GREEDY

- ☐ Size guard: if the exact route would be ILP and n exceeds ilp_max_tasks (default 150, add to config), route to CA-GREEDY and say so in the reason

- ☐ Optional flag simplified_always_dp (default false) which routes every simplified instance to WIS-DP

- ☐ reason text names the score, threshold, the five feature values, the dominant feature, and the rule that fired

- ☐ run_selected(instance) runs the chosen algorithm and stores the decision in AlgoResult.meta

4. Files / Modules Affected: src/rbp/selector/selector.py, config/defaults.yaml (ilp_max_tasks, simplified_always_dp), tests/test_selector.py.

5. Implementation Guidance: The literal D1 rule sends a simplified instance with a high score to CA-GREEDY even though WIS-DP is exact and cheap there. That is a consequence of the diagram in the spec, so the playbook keeps it as the default and exposes simplified_always_dp as the alternative. Decide D1 before building this milestone. The threshold is provisional (0.5) until 8.3.

6. Test Cases

| ID | Test Scenario | Preconditions | Steps | Expected Result | Status |
| --- | --- | --- | --- | --- | --- |
| T8.2-01 | Score equals threshold (edge) | score = threshold | Select | Exact route | ☐ |
| T8.2-02 | Just above threshold | score = threshold + 0.001 | Select | CA-GREEDY | ☐ |
| T8.2-03 | Low score, simplified | Simplified fixture | Select | WIS-DP | ☐ |
| T8.2-04 | Low score, extended, flag ilp | Extended fixture | Select | ILP-EXACT | ☐ |
| T8.2-05 | Low score, extended, flag none | Extended fixture | Select | CA-GREEDY with reason stating the flag | ☐ |
| T8.2-06 | ILP size guard | n above ilp_max_tasks | Select | CA-GREEDY, reason mentions size guard | ☐ |
| T8.2-07 | Always-DP flag | Simplified, high score, flag true | Select | WIS-DP | ☐ |
| T8.2-08 | Reason content | any | Read reason | Contains score, threshold, 5 feature names with values | ☐ |
| T8.2-09 | Determinism | none | Select twice | Same decision and text | ☐ |
| T8.2-10 | Missing threshold file (failure) | File removed | Select | Clear error | ☐ |
| T8.2-11 | Run and validate | 30 instances | run_selected then validator | 0 violations; meta contains decision | ☐ |
| T8.2-12 | Never routes WIS-DP to extended | 50 extended instances | Select | No WIS-DP decisions | ☐ |

7. Verification Checklist

- ☐ Boundary behaviour (T8.2-01, T8.2-02) confirmed

- ☐ Every decision's algorithm name exists in the runner registry

8. Milestone Completion Criteria: DONE when routing matches the chosen D1 rule on every test and each decision carries a complete reason.

9. Git Checkpoint

git status
git add .
git commit -m "feat(selector): threshold routing with decision reasoning"
git push origin phase-8-selector
git tag -a cp-8.2 -m "Milestone 8.2 stable" && git push origin cp-8.2

10. Rollback / Recovery: git revert <sha-of-8.2> (R2); previous stable cp-8.1.

## Milestone 8.3: Threshold and weight calibration

Depends on: 8.2, 6.2, 7.1; decision D2.

1. Milestone Name: Calibrate theta and alpha on calibration seeds, evaluate on held-out seeds.

2. Objective: Replace the provisional threshold with a measured one, without ML and without leaking evaluation data (spec: rule/threshold-based, 'learned' threshold).

3. Tasks to Complete

- ☐ Extend solve_ilp with deterministic_limit (CP-SAT max_deterministic_time) so calibration labels do not depend on machine speed

- ☐ scripts/calibrate_selector.py: build a suite from calibration seeds 1000-1099 over sizes 20-150 and a 3x3 grid of two knobs; label each instance exact_ok = 1 if ILP is OPTIMAL within the deterministic limit

- ☐ Choose theta by grid search (step 0.01) maximizing classification accuracy of score <= theta against exact_ok; if several theta tie, take the midpoint of the best range

- ☐ Optional alpha search: coordinate search on a 0.1-step simplex, same objective, calibration seeds only

- ☐ Assert calibration and evaluation seed ranges are disjoint; refuse evaluation seeds

- ☐ Write config/threshold.json (version >= 1, theta, alpha, calibration seeds, labelling limits, git hash, date)

- ☐ Held-out report on evaluation seeds 2000-2099 in reports/selector_eval.md: accuracy, majority-class baseline accuracy, objective and runtime of selector versus always-CA-GREEDY versus always-ILP

4. Files / Modules Affected: src/rbp/selector/calibration.py, scripts/calibrate_selector.py, config/threshold.json, reports/selector_eval.md, tests/test_calibration.py.

5. Implementation Guidance: Labelling by 'ILP solved to optimality within a fixed deterministic budget' ties the threshold to a measurable meaning: below it, exact solving is affordable. Report honestly if held-out accuracy does not beat the majority-class baseline; that is a finding about the five features, not a reason to tune on the evaluation set.

6. Test Cases

| ID | Test Scenario | Preconditions | Steps | Expected Result | Status |
| --- | --- | --- | --- | --- | --- |
| T8.3-01 | Grid search on synthetic labels | scores [0.1, 0.2, 0.8, 0.9], labels [1, 1, 0, 0] | Calibrate | theta in [0.2, 0.8), accuracy 1.0 | ☐ |
| T8.3-02 | All labels equal | all 1 | Calibrate | Valid theta returned, no crash | ☐ |
| T8.3-03 | Seed leakage (negative) | Evaluation seed passed to calibration | Calibrate | Raises error | ☐ |
| T8.3-04 | Determinism | Tiny suite, run twice | Compare JSON excluding date | Identical | ☐ |
| T8.3-05 | Deterministic ILP limit | Same instance on two runs | Solve with deterministic limit | Same status and objective | ☐ |
| T8.3-06 | Threshold file schema | Calibrated file | Load | Valid, version >= 1, alpha sums to 1 | ☐ |
| T8.3-07 | Placeholder rejected for release | version = 0 | Release check | Fails with message | ☐ |
| T8.3-08 | Held-out report | Evaluation seeds | Run report | File written with accuracy and baseline | ☐ |
| T8.3-09 | Regression of 8.2 | none | pytest tests/test_selector.py | Pass with new theta | ☐ |

7. Verification Checklist

- ☐ Calibration script reruns to the same threshold.json

- ☐ Evaluation seeds appear nowhere in calibration logs

- ☐ reports/selector_eval.md states the majority-class baseline next to the accuracy

8. Milestone Completion Criteria: DONE when theta and alpha come from the script, are versioned, and the held-out report exists.

9. Git Checkpoint

git status
git add .
git commit -m "feat(selector): calibrated threshold, deterministic ILP labelling, held-out report"
git push origin phase-8-selector
git tag -a cp-8.3 -m "Milestone 8.3 stable" && git push origin cp-8.3

Do NOT commit raw calibration run dumps under results/; commit only threshold.json and the short report.

10. Rollback / Recovery: git revert <sha-of-8.3> (R2) restores the previous threshold.json; previous stable cp-8.2.

## Phase 8 Completion Checkpoint

| Item | Record |
| --- | --- |
| Completed milestones | 8.1, 8.2, 8.3 |
| Tests passed | pytest ____ passed |
| Known issues | ____ (include held-out accuracy versus baseline) |
| Git commit / hash | ____; tag phase-8-complete |
| Overall phase verification | select() on 10 random instances returns a decision with a full reason; threshold file version >= 1 |
| Go / No-Go for Phase 9 | GO only if calibration is reproducible and the evaluation seeds were untouched |

git switch main && git merge --no-ff phase-8-selector -m "merge: phase 8"
git push origin main
git tag -a phase-8-complete -m "Phase 8 done" && git push origin phase-8-complete
git switch -c phase-9-experiments

# Phase 9: Experiments and Analysis

## Milestone 9.1: Experiment runner and results storage

Depends on: Phase 8 complete; decision D11.

1. Milestone Name: Reproducible, resumable experiment grid runner.

2. Objective: Run any algorithm set over a grid of sizes, seeds and knob levels and store results with full provenance (spec sections 4.2 and 5.3).

3. Tasks to Complete

- ☐ Experiment config files config/experiments/e1.yaml, e2.yaml, e3.yaml (id, instance kind, sizes, seeds, knob levels, algorithms, ILP limit)

- ☐ run_grid(cfg) writes results/<id>/runs.csv (one row per run, columns from RunRecord), meta.json (git hash and dirty flag, config hash, Python and ortools versions, timestamp) and failures.log

- ☐ SELECTOR registered as an algorithm that logs the algorithm it chose

- ☐ Resume: skip rows already present for the same (algorithm, size, knob, seed)

- ☐ Failure isolation: one failing run is recorded and the grid continues

- ☐ Runs execute serially (parallel timing would distort runtime results)

- ☐ Evaluation experiments may only use evaluation seeds

4. Files / Modules Affected: src/rbp/experiments/runner.py, config/experiments/*.yaml, tests/test_runner.py.

5. Implementation Guidance: Every run passes through run_algorithm, so the independent validator checks every schedule that enters a result table. results/ is gitignored; summary tables are generated later and committed.

6. Test Cases

| ID | Test Scenario | Preconditions | Steps | Expected Result | Status |
| --- | --- | --- | --- | --- | --- |
| T9.1-01 | Row count | Grid 2 algorithms x 2 sizes x 3 seeds | Run | 12 rows | ☐ |
| T9.1-02 | Reproducibility | none | Run twice | Equal in all columns except runtime and timestamp | ☐ |
| T9.1-03 | Resume | Kill after 5 rows | Rerun | Remaining rows added, no duplicates | ☐ |
| T9.1-04 | Algorithm exception | Inject failing algorithm | Run | Row with status ERROR, grid completes | ☐ |
| T9.1-05 | ILP time limit | Tiny limit | Run | Status recorded, optimal = False | ☐ |
| T9.1-06 | Violations flagged | Inject invalid schedule | Run | Row stored with violations > 0 | ☐ |
| T9.1-07 | Provenance | none | Read meta.json | Git hash, config hash, versions present | ☐ |
| T9.1-08 | Seed policy (negative) | Evaluation experiment with calibration seeds | Run | Refused | ☐ |
| T9.1-09 | Schema | none | Read CSV | Expected columns and types | ☐ |
| T9.1-10 | Selector logging | SELECTOR rows | Inspect | Chosen algorithm column filled | ☐ |

7. Verification Checklist

- ☐ Tiny grid runs end to end from the command line: python -m rbp.experiments.runner config/experiments/e1.yaml --dry-run

- ☐ git status shows results/ untracked and ignored

8. Milestone Completion Criteria: DONE when a grid is reproducible, resumable, failure-tolerant and carries provenance.

9. Git Checkpoint

git status
git add .
git commit -m "feat(experiments): reproducible resumable runner with provenance"
git push origin phase-9-experiments
git tag -a cp-9.1 -m "Milestone 9.1 stable" && git push origin cp-9.1

Do NOT commit results/.

10. Rollback / Recovery: git revert <sha-of-9.1> (R2); previous stable phase-8-complete.

## Milestone 9.2: Experiments E1, E2, E3 and analysis

Depends on: 9.1.

1. Milestone Name: Optimality gap, scalability and conflict-density studies.

2. Objective: Produce the measured trade-off between solution quality and computational cost (spec section 3.2 item 5), reporting gaps only where a genuine optimum exists.

3. Tasks to Complete

- ☐ E1 optimality gap: sizes 20, 40, 80, 120; evaluation seeds 2000-2029; algorithms NAIVE-GREEDY, CA-GREEDY, SELECTOR, ILP-EXACT (reference), plus WIS-DP on simplified instances

- ☐ E2 scalability: n in 50, 100, 200, 500, 1000, 2000, 5000; 5 seeds; NAIVE-GREEDY, CA-GREEDY, WIS-DP (simplified), ILP-EXACT while it solves within its limit

- ☐ E3 conflict density: 5 levels of assets_per_corridor (8, 6, 4, 3, 2), n=100, 30 seeds; record objective ratio, gap, selector decisions

- ☐ analysis.py: mean and standard deviation per cell, paired CA-minus-naive differences with win/tie/loss counts, share of instances where ILP was OPTIMAL

- ☐ Figures with matplotlib in reports/figures/: gap versus size, runtime versus n on log-log axes with fitted slope, objective ratio versus density, selector decision share per density level

- ☐ Commit small summary CSVs reports/summary_E1.csv to E3.csv

- ☐ Reproducibility check: rerun each experiment and compare objective columns; compare the two seed halves for consistency

4. Files / Modules Affected: src/rbp/experiments/analysis.py, scripts/make_report.py, reports/figures/*.png, reports/summary_E*.csv, tests/test_analysis.py.

5. Implementation Guidance: Optimality gap needs a proven optimum, so E1 and E3 compute gaps only for rows where ILP status is OPTIMAL, and the report states how many rows that is. Beyond that size the comparison is relative (objective ratio), never called a gap. Expected complexity trends to check: WIS-DP about n log n (log-log slope close to 1), greedy methods polynomial, ILP growing quickly until it hits its limit.

6. Test Cases

| ID | Test Scenario | Preconditions | Steps | Expected Result | Status |
| --- | --- | --- | --- | --- | --- |
| T9.2-01 | Aggregation math | Fixture CSV with known values | Aggregate | Mean and std equal hand values | ☐ |
| T9.2-02 | Win/tie/loss | Fixture pairs | Count | Correct counts | ☐ |
| T9.2-03 | Gap only on OPTIMAL | Fixture with FEASIBLE rows | Aggregate gap | Those rows excluded, count reported | ☐ |
| T9.2-04 | Slope fit | Synthetic runtimes y = x log x | Fit | Slope between 0.9 and 1.3 | ☐ |
| T9.2-05 | Figures created | Fixture results | Run report | Non-empty PNG files | ☐ |
| T9.2-06 | Zero anomalies | Real E1 run | Count anomaly rows | 0 | ☐ |
| T9.2-07 | Zero violations | All E1-E3 rows | Sum violations | 0 | ☐ |
| T9.2-08 | Reproducibility | Rerun E1 | Compare objective columns | Identical | ☐ |
| T9.2-09 | Empty cell handling | A cell with all ERROR rows | Aggregate | Reported as missing, no crash | ☐ |
| T9.2-10 | Summary schema | Summary CSVs | Read | Required columns present | ☐ |

7. Verification Checklist

- ☐ E1 to E3 complete with 0 anomalies and 0 violations

- ☐ Report lists the number of rows behind every plotted point

- ☐ Every claim in the report is backed by a figure or table in reports/

8. Milestone Completion Criteria: DONE when all three experiments run reproducibly, figures and summaries exist, and the report marks which numbers are true gaps.

9. Git Checkpoint

git status
git add .
git commit -m "feat(experiments): E1-E3 studies, analysis and report figures"
git push origin phase-9-experiments
git tag -a cp-9.2 -m "Milestone 9.2 stable" && git push origin cp-9.2

Do NOT commit results/ raw CSVs or any figure larger than a few hundred KB.

10. Rollback / Recovery: git revert <sha-of-9.2> (R2); previous stable cp-9.1. Raw results can always be regenerated from the committed configs and seeds.

## Phase 9 Completion Checkpoint

| Item | Record |
| --- | --- |
| Completed milestones | 9.1, 9.2 |
| Tests passed | pytest ____ passed; E1-E3 anomalies 0, violations 0 |
| Known issues | ____ |
| Git commit / hash | ____; tag phase-9-complete |
| Overall phase verification | Rerun E1 on a second machine or fresh clone: objective columns identical |
| Go / No-Go for Phase 10 | GO only if results are reproducible and the summary tables are committed |

git switch main && git merge --no-ff phase-9-experiments -m "merge: phase 9"
git push origin main
git tag -a phase-9-complete -m "Phase 9 done" && git push origin phase-9-complete
git switch -c phase-10-ui

# Phase 10: Streamlit Prototype

## Milestone 10.1: API facade and Streamlit shell

Depends on: Phase 9 complete.

1. Milestone Name: UI shell over a scheduling-free facade (functional requirement 9).

2. Objective: A working prototype that generates or loads an instance, runs algorithms, and shows validation status and metrics, with zero scheduling logic in the UI.

3. Tasks to Complete

- ☐ src/rbp/api.py facade: generate_instance, load_instance, list_algorithms, run, compare, select; returns plain dataclasses or dicts

- ☐ app/streamlit_app.py: sidebar for instance source (generate with kind, n, corridors, seed; or upload JSON) and algorithm choice; Run button; validation status; metrics table

- ☐ st.cache_data keyed by instance hash, algorithm and config so repeated clicks do not re-run ILP

- ☐ UI limits from config: max_tasks_ui, upload size cap (server.maxUploadSize in .streamlit/config.toml), ILP disabled above ilp_max_tasks with an explanation

- ☐ Update the boundary test: app/ may import only rbp.api, rbp.viz, streamlit, pandas, matplotlib

4. Files / Modules Affected: src/rbp/api.py, app/streamlit_app.py, .streamlit/config.toml, tests/test_api.py, tests/test_app.py, tests/test_import_boundaries.py.

5. Implementation Guidance: Streamlit is needed because the spec asks for a prototype that displays results. The facade keeps the boundary from spec section 5.3 (separation between algorithms, validation, experiments and UI). Uploaded files are parsed with json only, never eval, pickle or yaml.load on user data.

6. Test Cases

| ID | Test Scenario | Preconditions | Steps | Expected Result | Status |
| --- | --- | --- | --- | --- | --- |
| T10.1-01 | Default launch | AppTest.from_file | Run | No exception | ☐ |
| T10.1-02 | Generate and run | seed 3, CA-GREEDY | Click Run | Metrics table shown, violations 0 | ☐ |
| T10.1-03 | Reproducible UI | Same seed twice | Run both | Same objective | ☐ |
| T10.1-04 | Invalid upload (failure) | JSON with duration -1 | Upload | Error message listing E_DURATION, no traceback | ☐ |
| T10.1-05 | Malformed upload | Truncated JSON | Upload | Friendly error | ☐ |
| T10.1-06 | Oversized upload (security) | File above cap | Upload | Rejected | ☐ |
| T10.1-07 | Task limit (security) | n above max_tasks_ui | Run | Refused with message | ☐ |
| T10.1-08 | WIS-DP on extended | Extended instance | Choose WIS-DP | Shows not applicable, no crash | ☐ |
| T10.1-09 | ILP guard | n above ilp_max_tasks | Choose ILP | Disabled with explanation | ☐ |
| T10.1-10 | No logic in UI | none | Boundary test and grep for rbp.algorithms in app/ | 0 hits | ☐ |
| T10.1-11 | API returns plain data | each facade call | json.dumps the result | Serializable | ☐ |
| T10.1-12 | No unsafe parsing | none | grep for eval(, pickle, exec( | 0 hits in src/ and app/ | ☐ |

7. Verification Checklist

- ☐ streamlit run app/streamlit_app.py opens, runs one generated instance end to end

- ☐ Boundary test green with the updated rule

8. Milestone Completion Criteria: DONE when the app works end to end through the facade and all failure inputs end in messages, not tracebacks.

9. Git Checkpoint

git status
git add .
git commit -m "feat(ui): API facade and Streamlit shell with input limits"
git push origin phase-10-ui
git tag -a cp-10.1 -m "Milestone 10.1 stable" && git push origin cp-10.1

Do NOT commit .streamlit/secrets.toml (none is needed) or uploaded test files.

10. Rollback / Recovery: git revert <sha-of-10.1> (R2); previous stable phase-9-complete.

## Milestone 10.2: Gantt chart, comparison and selector reasoning views

Depends on: 10.1.

1. Milestone Name: Result visualisation (functional requirements 8, 9 and 10).

2. Objective: Show schedules as Gantt charts, compare algorithms side by side, and display the selector's reasoning.

3. Tasks to Complete

- ☐ src/rbp/viz/gantt.py: gantt_figure(instance, schedule, show_trains=True) with matplotlib; rows per corridor and asset, bars coloured by criticality, train intervals shaded; unscheduled tasks returned as a table

- ☐ Compare tab: run chosen algorithms; table of objective, coverage, runtime, violations, gap (only against a genuine optimum), plus an objective bar chart

- ☐ Selector tab: five feature values as a bar chart, score against threshold, chosen algorithm, reason text from select()

- ☐ ILP time-limit control defaulting to the config value

- ☐ Always plt.close(fig) after rendering

- ☐ What-if analysis stays out of scope (the spec marks it as later)

4. Files / Modules Affected: src/rbp/viz/gantt.py, app/streamlit_app.py, tests/test_viz.py, tests/test_app.py.

5. Implementation Guidance: Figures are produced by viz, not by the app, so they can be unit-tested and reused for the report. Colour is never the only carrier of meaning: show criticality in the hover or table as well.

6. Test Cases

| ID | Test Scenario | Preconditions | Steps | Expected Result | Status |
| --- | --- | --- | --- | --- | --- |
| T10.2-01 | Empty schedule | none scheduled | gantt_figure | Figure with 0 bars, no error | ☐ |
| T10.2-02 | Bar count | 20 scheduled tasks | Count bars | 20 | ☐ |
| T10.2-03 | Train shading | 5 train intervals shown | Count patches | 5 | ☐ |
| T10.2-04 | Scale | 1000 tasks | Time render | Under 10 s | ☐ |
| T10.2-05 | Comparison table | 4 algorithms | Run compare | One row each; NOT_APPLICABLE shown as status | ☐ |
| T10.2-06 | Gap shown only with optimum | Heuristics only selected | Compare | Gap column empty with note | ☐ |
| T10.2-07 | Selector reasoning matches | any instance | Compare UI text with select().reason | Identical | ☐ |
| T10.2-08 | ILP failure path | Mock ILP error | Run | Message shown, other results intact | ☐ |
| T10.2-09 | All tabs render | AppTest | Visit each tab | No exception | ☐ |
| T10.2-10 | Figure cleanup | 20 reruns | Count open matplotlib figures | 0 | ☐ |
| T10.2-11 | Regression of 10.1 | none | pytest tests/test_app.py tests/test_api.py | Pass | ☐ |

7. Verification Checklist

- ☐ Manual walkthrough: generate, run NAIVE and CA, compare, open selector tab

- ☐ Gantt bars match the schedule table row for row on one sample

8. Milestone Completion Criteria: DONE when all three views work, failure paths show messages, and figures are cleaned up.

9. Git Checkpoint

git status
git add .
git commit -m "feat(ui): Gantt, comparison and selector reasoning views"
git push origin phase-10-ui
git tag -a cp-10.2 -m "Milestone 10.2 stable" && git push origin cp-10.2

10. Rollback / Recovery: git revert <sha-of-10.2> (R2); previous stable cp-10.1.

## Phase 10 Completion Checkpoint

| Item | Record |
| --- | --- |
| Completed milestones | 10.1, 10.2 |
| Tests passed | pytest ____ passed |
| Known issues | ____ |
| Git commit / hash | ____; tag phase-10-complete |
| Overall phase verification | Demo script: generate, run all algorithms, compare, view Gantt and selector reasoning, upload an invalid file |
| Go / No-Go for Phase 11 | GO only if every failure input ends in a message and the boundary test is green |

git switch main && git merge --no-ff phase-10-ui -m "merge: phase 10"
git push origin main
git tag -a phase-10-complete -m "Phase 10 done" && git push origin phase-10-complete
git switch -c phase-11-release

# Phase 11: Documentation, Reproducibility and Release

## Milestone 11.1: Documentation, one-command reproduction and release check

Depends on: Phase 10 complete.

1. Milestone Name: Deployment-ready, documented and reproducible release.

2. Objective: Anyone can install, test, reproduce the results and launch the app from the README alone (spec non-functional requirements: reproducible experiments, complexity documentation).

3. Tasks to Complete

- ☐ README.md: install, run tests, run the 100/100 gate, run experiments, launch the app, repository map

- ☐ docs/COMPLEXITY.md: WIS-DP O(n log n) time and O(n) space; NAIVE-GREEDY and CA-GREEDY bounds derived from your implementation (candidates per task, feasibility cost O(duration), look-ahead cost O(k x m)); ILP worst case exponential; selector feature extraction O(n log n)

- ☐ docs/VALIDATION.md: gates passed with dates and commit hashes (links to docs/validation_log.md)

- ☐ scripts/reproduce.sh: full tests, gate, E1-E3, summary CSVs

- ☐ scripts/release_check.py: threshold version >= 1; golden hashes present; no tracked results/ or data/generated/; no secret-like patterns in tracked files; relative doc links resolve

- ☐ Pin final requirements.txt; .streamlit/config.toml with headless = true

- ☐ Deployment: Streamlit Community Cloud needs only requirements.txt and the entry file app/streamlit_app.py. No Dockerfile is added because the spec does not require containers; add one only if your course asks for it.

4. Files / Modules Affected: README.md, docs/COMPLEXITY.md, docs/VALIDATION.md, scripts/reproduce.sh, scripts/release_check.py, requirements.txt, .streamlit/config.toml, tests/test_release_check.py.

5. Implementation Guidance: State each complexity claim next to the code that earns it, and say plainly that CA-GREEDY is a heuristic with no optimality guarantee (spec). Do not describe the selector as machine learning.

6. Test Cases

| ID | Test Scenario | Preconditions | Steps | Expected Result | Status |
| --- | --- | --- | --- | --- | --- |
| T11.1-01 | Fresh-clone install | New directory, new venv | Follow README commands only | Tests pass | ☐ |
| T11.1-02 | One-command reproduction | Fresh clone | bash scripts/reproduce.sh | Summary CSVs identical to committed (git diff clean) | ☐ |
| T11.1-03 | Release check passes | Final state | python scripts/release_check.py | Exit 0 | ☐ |
| T11.1-04 | Placeholder threshold (negative) | version = 0 | Release check | Fails with message | ☐ |
| T11.1-05 | Tracked-file scan (negative) | Temporarily git add -f results/x.csv | Release check | Fails; then unstage | ☐ |
| T11.1-06 | Secret scan | Tracked files | grep for key, token, secret patterns | 0 findings | ☐ |
| T11.1-07 | Link check | Docs | Release check link step | All relative links resolve | ☐ |
| T11.1-08 | App health | Clean venv | streamlit run app/streamlit_app.py --server.headless true, request /_stcore/health | HTTP 200 and text ok | ☐ |
| T11.1-09 | Full test suite | Clean venv | pytest including slow | All pass | ☐ |

7. Verification Checklist

- ☐ A teammate who has not seen the repo completes T11.1-01 to T11.1-03 using only the README

- ☐ docs/COMPLEXITY.md claims match measured slopes from E2

8. Milestone Completion Criteria: DONE when the release check passes and a second person reproduces results from a fresh clone.

9. Git Checkpoint

git status
git add .
git commit -m "docs: README, complexity notes, reproduction script and release check"
git push origin phase-11-release
git tag -a cp-11.1 -m "Milestone 11.1 stable" && git push origin cp-11.1

10. Rollback / Recovery: git revert <sha-of-11.1> (R2); previous stable phase-10-complete.

## Phase 11 Completion Checkpoint and Release Tag

| Item | Record |
| --- | --- |
| Completed milestones | 11.1 |
| Tests passed | Full pytest ____ passed; release check exit 0 |
| Known issues | ____ |
| Git commit / hash | ____; tag v1.0.0 |
| Overall phase verification | Final Release Checklist below fully ticked |
| Go / No-Go for release | GO only if every checklist item is ticked or has a written, accepted exception |

git switch main && git merge --no-ff phase-11-release -m "merge: phase 11 release"
git push origin main
git tag -a v1.0.0 -m "Release 1.0.0" && git push origin v1.0.0

# Final Release Checklist

Functionality

- ☐ All ten functional requirements work (traceability table below)

- ☐ WIS-DP, NAIVE-GREEDY, CA-GREEDY, ILP-EXACT, BRUTE-FORCE and the selector run through run_algorithm

- ☐ The selector always returns a reason, and its rule matches the decision recorded for D1

Testing

- ☐ pytest (including slow tests) passes on a clean venv and on CI

- ☐ WIS-DP versus brute force: 100/100; brute force = WIS-DP = ILP: 100/100

- ☐ Predicate-versus-validator fuzz: 0 disagreements

- ☐ Every schedule in E1-E3 has 0 violations and 0 anomalies

- ☐ Same seed gives identical objectives across reruns (golden hashes and E1 rerun)

Security

- ☐ No secrets, keys or .env files tracked: git ls-files | grep -iE "\.env|secret|key" returns nothing relevant

- ☐ Uploads are size-limited and parsed with json only; no eval, exec or pickle in src/ or app/

- ☐ Dependencies pinned in requirements.txt

- ☐ Scope note: the project has no authentication or authorization. If the app is later exposed publicly with user accounts, add that as a new phase with unauthorized-access tests before release.

Performance

- ☐ E2 results recorded; WIS-DP slope near 1 on log-log axes

- ☐ ILP always runs under its configured limit; time-limited results are labelled non-optimal

- ☐ UI renders a 1000-task Gantt in under 10 s

Deployment

- ☐ streamlit run app/streamlit_app.py works from a fresh clone

- ☐ Health check returns HTTP 200

- ☐ threshold.json has version >= 1 and records its calibration seeds

Documentation

- ☐ README, docs/ARCHITECTURE.md, docs/COMPLEXITY.md, docs/GENERATOR.md, docs/CA_GREEDY.md, docs/VALIDATION.md, docs/ilp_crosscheck.md, reports/selector_eval.md exist and are current

- ☐ Open decisions D1-D12 are recorded with the choice made

- ☐ Report states which numbers are true optimality gaps and which are relative comparisons

Git repository cleanliness

- ☐ git status clean on main; main equals origin/main

- ☐ Tags cp-*, phase-*-complete and v1.0.0 pushed

- ☐ git ls-files contains no .venv, caches, results/, data/generated/, large binaries

- ☐ CI green on the release commit

## Appendix: Requirement traceability

| Spec functional requirement | Milestones |
| --- | --- |
| 1 Generate or load instances | 1.3, 3.1, 3.2, 3.3 |
| 2 Represent tasks, corridors, resources, trains | 1.1 |
| 3 Validate input data | 1.2 |
| 4 Check scheduling constraints | 2.1 |
| 5 Generate schedules with different algorithms | 4.1, 5.1, 5.2, 5.3, 6.1 |
| 6 Validate schedules independently | 2.2 |
| 7 Calculate scheduling metrics | 7.1 |
| 8 Compare algorithm performance | 9.1, 9.2, 10.2 |
| 9 Display results through a prototype | 10.1, 10.2 |
| 10 Reasoning behind adaptive selection | 8.1, 8.2, 8.3 |